## README
Sample Field Inputs (Synthetic): Urban Garbage Treatment Plant, Construction Contractor
What this is | Realistic, deliberately imperfect site updates for 4 Oct to 8 Dec 2027, written the way supervisors and site engineers actually report. They are consistent with the L4-L6 Schedule workbook (same project, same activities) but never quote Activity IDs.
Sheets | Text_Reports: 46 WhatsApp messages and typed daily-report lines. Civil_DPR: a civil daily progress sheet (quantity and cumulative quantity). Fabrication_Log: piping spool and structural steel yard log. Electrical_Log: earthing and temporary works log.
Your task (students) | Extract activity-level start and finish events and progress from these inputs and link each to the correct Activity ID in the L4-L6 Schedule workbook. Do not assume every item has a match, and do not assume every date is stated.
What to expect | Different words for the same work, several activities in one message, work described in finer detail than the plan, dates given as "today" or "tomorrow" or not at all, locations that are ambiguous, work that is not in the plan, and delay reasons without any start or finish.
Timestamps | Date and Time on Text_Reports are the message timestamps. Two records have no date or time. For all other sheets the Date column is the work date.
Not included | No answer key here. Organisers hold a separate key. Do not treat the content as a complete list of what happened on site: activities not mentioned are simply not reported yet.
Data status | All content is synthetic and for the hackathon only. Quantities and names are invented. Spelling and phrasing are intentionally informal.

## Text_Reports
Msg ID | Date | Time | Channel | From (role) | Message
TXT-001 | 2027-10-04 | 12:30 | WhatsApp | Site Engineer (Contractor) | PMC team reached site 10 am. Handover started, joint survey of boundary going on.
TXT-002 | 2027-10-05 | 17:45 | WhatsApp | Site Engineer (Contractor) | Joint survey finished. Site handover minutes signed by both sides.
TXT-003 | 2027-10-06 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | Started marking for site office and store shed. Temporary fencing gang started from gate side. Survey team started fixing benchmark pillars.
TXT-004 | 2027-10-08 | 17:30 | WhatsApp | Site Engineer (Contractor) | DG set 125 kVA reached site and unloaded. Labour camp shed erection started. QAP and ITP submitted to PMC today.
TXT-005 | 2027-10-09 | 18:10 | WhatsApp | Civil Supervisor | Fencing 300 m complete, signage boards fixed, gate hung.
TXT-006 | 2027-10-11 | 17:50 | WhatsApp | Survey Engineer | 12 nos BM pillars fixed, levels checked, PMC signed level book.
TXT-007 | 2027-10-13 | 18:20 | Daily report (typed) | Site Engineer (Contractor) | Site office and stores completed today. Furniture placed.
TXT-008 | 2027-10-15 | 16:40 | WhatsApp | Site Engineer (Contractor) | Excavator 2 nos and JCB arrived. 20T crane will reach on 19th.
TXT-009 | 2027-10-15 | 18:00 | WhatsApp | HSE Officer | Safety plan approved by PMC today. Induction starts tomorrow.
TXT-010 | 2027-10-16 | 17:30 | Daily report (typed) | Site Engineer (Contractor) | Labour camp ready for 120 workers, canteen shed also ready. Temporary power through DG done, water tanker arranged.
TXT-011 | 2027-10-18 | 17:00 | WhatsApp | HSE Officer | Safety induction for 85 workers done.
TXT-012 | 2027-10-18 | 17:40 | WhatsApp | QC Engineer | Lab set up complete. Cube moulds, sieve set, slump cone, balance installed.
TXT-013 | 2027-10-19 | 16:50 | WhatsApp | Site Engineer (Contractor) | 20T crane reached site and unloaded. All equipment available now.
TXT-014 | 2027-10-20 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | Site clearing started with 2 JCB and 6 tippers. Also started making temporary haul road with murrum for tippers.
TXT-015 | 2027-10-22 | 17:30 | WhatsApp | QC Engineer | QAP and ITP approved by PMC (comments incorporated).
TXT-016 | 2027-10-27 | 18:00 | WhatsApp | Civil Supervisor | Site clearing finished. Debris shifting to dump yard also done.
TXT-017 | 2027-10-28 | 18:30 | Daily report (typed) | Site Engineer (Contractor) | Started cut and fill from north side. Boundary wall trench marking done, excavation started on east side. Structural steel PO placed with mill, dispatch in 3 weeks.
TXT-018 | 2027-10-30 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | Cut and fill 3500 m3 done till date. Boundary trench east and north side done, about 700 m of 1200 m.
TXT-019 | 2027-11-02 | 17:30 | WhatsApp | Piping Supervisor | Pipes for spools not received from vendor yet. Prefab yard and welding machines ready.
TXT-020 | 2027-11-04 | 16:30 | WhatsApp | Piping Supervisor | First lot of pipes came today. Spool fabrication will start tomorrow.
TXT-021 | 2027-11-06 | 18:15 | Daily report (typed) | Site Engineer (Contractor) | Boundary wall trench excavation completed all sides, 1200 m. Rain in the evening.
TXT-022 | 2027-11-08 | 17:45 | WhatsApp | Civil Supervisor | PCC in boundary wall trench started, 60 m done.
TXT-023 | 2027-11-12 | 16:00 | WhatsApp | Site Engineer (Contractor) | Heavy rain from 2 pm, all earthwork stopped. Tippers stuck at fill area.
TXT-024 | 2027-11-12 | 17:30 | WhatsApp | Store Keeper | Structural steel lot 1 received, 90 MT (angles, channels). Balance 150 MT later.
TXT-025 | 2027-11-15 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | Cut and fill finished, FGL achieved as per drawing. Compaction to start tomorrow.
TXT-026 | 2027-11-16 | 17:30 | WhatsApp | QC Engineer | Compaction started with 2 rollers. FDD samples taken.
TXT-027 | 2027-11-19 | 18:20 | Daily report (typed) | Site Engineer (Contractor) | Compaction complete, density test 98% passed. Balance steel 150 MT received, all steel lots now at site.
TXT-028 | 2027-11-20 | 18:00 | WhatsApp | Piping Supervisor | All spools 180 nos fabricated and visually checked by QC.
TXT-029 | 2027-11-20 | 18:10 | WhatsApp | Civil Supervisor | Boundary wall PCC and footing done for full length.
TXT-030 | 2027-11-22 | 18:30 | Daily report (typed) | Site Engineer (Contractor) | Brick masonry of boundary wall started east side. Excavation started for receiving hall footings, processing building footings, RDF shed footings and admin block foundation.
TXT-031 | 2027-11-23 | 18:00 | WhatsApp | Civil Supervisor | Pit excavation started with sheet piling. Water seepage seen at 2 m depth, 2 dewatering pumps placed.
TXT-032 | 2027-11-24 | 18:10 | Daily report (typed) | Site Engineer (Contractor) | Compost yard levelling started. Substation room excavation begun. Drain trench excavation started, 80 m done.
TXT-033 | 2027-11-25 | 18:00 | WhatsApp | Civil Supervisor | Admin block foundation excavation done. Sump excavation started. Road subgrade preparation started near gate.
TXT-034 | 2027-11-26 | 17:50 | WhatsApp | Civil Supervisor | RDF shed footing pits F1 to F14 all excavated. Fire water tank excavation started.
TXT-035 | 2027-11-27 | 17:40 | WhatsApp | Civil Supervisor | Hall footing excavation 60% done.
TXT-036 | 2027-11-29 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | Compost yard levelling completed, 6000 sqm. Weighbridge foundation work started.
TXT-037 | 2027-11-30 | 18:20 | Daily report (typed) | Site Engineer (Contractor) | Receiving hall footing excavation completed, 12 footings. PCC started in RDF shed footings. Sump excavation completed.
TXT-038 | 2027-12-01 | 17:30 | WhatsApp | Civil Supervisor | Tipping hall PCC started. Road subgrade prep complete, 6000 sqm.
TXT-039 | 2027-12-02 | 17:45 | WhatsApp | Electrical Supervisor | Earthing pits started, 6 nos ready. Temporary lighting installed near pit and yard, 12 poles.
TXT-040 | 2027-12-02 | 18:00 | WhatsApp | Civil Supervisor | Processing bldg excavation complete, 3100 cum.
TXT-041 | 2027-12-03 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | PCC laid for tipping hall footings, 110 cum done. PCC started in processing building from grid A.
TXT-042 | 2027-12-04 | 18:10 | WhatsApp | Civil Supervisor | Pit excavation completed to final level. Dewatering still on. PCC done in processing building footings.
TXT-043 | 2027-12-06 | 18:00 | Daily report (typed) | Site Engineer (Contractor) | Boundary wall masonry 250 m done, half day lost in rain. Rebar tying started in processing building footings.
TXT-044 | 2027-12-07 | 17:40 | WhatsApp | Civil Supervisor | Pit raft rebar work started, 12 MT tied. Today concrete 45 cum, RMC 8 trucks.
TXT-045 |  |  | WhatsApp (export, timestamp missing) | Civil Supervisor | Brick masonry east side finished, starting south side.
TXT-046 |  |  | Site diary (transcribed from scan) | Civil Supervisor | Drain trench excavation completed, 900 RM total.

## Civil_DPR
Rec ID | Date | Area / Location | Work description | Qty today | Unit | Cumulative qty | Manpower / equipment | Remarks
CIV-001 | 2027-11-22 | Rcvg Hall | Footing excavation F1-F3 | 350 | cum | 350 | Helper 14, JCB 2, Tipper 4
CIV-002 | 2027-11-23 | Rcvg Hall | Footing excavation F4-F6 | 400 | cum | 750 | Helper 14, JCB 2, Tipper 4
CIV-003 | 2027-11-26 | Rcvg Hall | Footing excavation F9-F10 | 350 | cum | 1800 | Helper 12, JCB 2, Tipper 4
CIV-004 | 2027-11-30 | Rcvg Hall | Footing excavation F12, trimming | 200 | cum | 2200 | Helper 10, JCB 1 | Completed
CIV-005 | 2027-11-22 | Proc. bldg | Excavation grid A-C | 250 | cum | 250 | Helper 16, JCB 2, Tipper 5
CIV-006 | 2027-11-25 | Proc. bldg | Excavation grid D-F | 320 | cum | 1200 | Helper 16, JCB 2, Tipper 5
CIV-007 | 2027-11-27 | Proc. bldg | Excavation grid G-H | 330 | cum | 1860 | Helper 16, JCB 2, Tipper 5 | 60% of total
CIV-008 | 2027-11-30 | Proc. bldg | Excavation trimming | 330 | cum | 2540 | Helper 14, JCB 2, Tipper 4
CIV-009 | 2027-12-02 | Proc. bldg | Excavation, final level | 260 | cum | 3100 | Helper 12, JCB 2, Tipper 4 | Ready for PCC
CIV-010 | 2027-11-23 | Pit (hopper) | Excavation with sheet piling | 150 | cum | 150 | Helper 10, Excavator 1 | Seepage, 2 pumps running
CIV-011 | 2027-11-26 | Pit (hopper) | Excavation | 150 | cum | 650 | Helper 10, Excavator 1
CIV-012 | 2027-11-30 | Pit (hopper) | Excavation | 100 | cum | 1010 | Helper 10, Excavator 1
CIV-013 | 2027-12-03 | Pit (hopper) | Excavation | 150 | cum | 1380 | Helper 10, Excavator 1
CIV-014 | 2027-12-04 | Pit (hopper) | Excavation, final level | 120 | cum | 1500 | Helper 10, Excavator 1 | Final level reached
CIV-015 | 2027-11-22 | RDF shed | Footing pit excavation | 120 | cum | 120 | Helper 8, JCB 1
CIV-016 | 2027-11-26 | RDF shed | Footing pit excavation F11-F14 | 120 | cum | 600 | Helper 8, JCB 1 | Completed
CIV-017 | 2027-11-22 | Admin block | Foundation excavation | 70 | cum | 70 | Helper 6, JCB 1
CIV-018 | 2027-11-25 | Admin block | Foundation excavation | 70 | cum | 300 | Helper 6, JCB 1 | Completed
CIV-019 | 2027-11-22 | B/wall east | Brick masonry | 30 | RM | 30 | Mason 6, Helper 8
CIV-020 | 2027-11-30 | B/wall east | Brick masonry | 40 | RM | 130 | Mason 8, Helper 10
CIV-021 | 2027-12-06 | B/wall | Brick masonry | 45 | RM | 250 | Mason 8, Helper 10 | Rain half day
CIV-022 | 2027-11-24 | Storm drain | Trench excavation | 80 | RM | 80 | Helper 12, JCB 1
CIV-023 | 2027-12-01 | Storm drain | Trench excavation | 110 | RM | 560 | Helper 12, JCB 1
CIV-024 | 2027-12-06 | Storm drain | Trench excavation | 100 | RM | 760 | Helper 12, JCB 1
CIV-025 | 2027-12-07 | RDF shed | RMC pour footings F1-F6 | 45 | cum | 45 | Mason 4, Helper 12, Pump 1 | 8 trucks RMC

## Fabrication_Log
Rec ID | Date | Item / Mark no. | Description | Qty | Unit | Status | Remarks
FAB-001 | 2027-11-04 | PIPE-LOT1 | CS pipes 6", 8", 10" lot 1 received | 60 | spool eq. | Received | Store yard
FAB-002 | 2027-11-05 | S-001 to S-012 | Cut and fit-up | 12 | spools | In progress | Fabrication started
FAB-003 | 2027-11-09 | S-001 to S-040 | Welded, visual OK | 40 | spools | In progress
FAB-004 | 2027-11-12 | STL-LOT1 | Angles, channels, plates received | 90 | MT | Received | Balance 150 MT expected 19-Nov
FAB-005 | 2027-11-16 | S-001 to S-110 | Welded, visual OK | 110 | spools | In progress
FAB-006 | 2027-11-19 | STL-LOT2 | Balance structural steel received | 150 | MT | Received | All steel received
FAB-007 | 2027-11-20 | S-001 to S-180 | All welded, QC visual done | 180 | spools | Completed

## Electrical_Log
Rec ID | Date | Location | Work description | Qty | Unit | Remarks
ELE-001 | 2027-12-02 | Near substation | Earth pit E1-E6 (GI pipe electrode) complete | 6 | Nos
ELE-002 | 2027-12-02 | Pit and yard area | Temporary lighting poles with LED flood lights | 12 | Nos | Temporary works
ELE-003 | 2027-12-04 | Process bldg periphery | Earth pit E7-E12 complete | 6 | Nos | Cumulative 12
ELE-004 | 2027-12-07 | Boundary side | GI strip 50x6 laid and welded | 120 | RM