## README
Construction Contractor L4-L5-L6 Schedule (Synthetic Case)
Purpose | Teaching dataset for the hackathon: shows how executor-level work (L5/L6 tasks reported by supervisors) hangs under the planner's L3/L4 nodes in Primavera P6, and gives a common ground truth to test extraction and schedule-linking.
Case project | Urban garbage treatment plant (100 TPD: segregation, composting, RDF), Town XYZ, by Company ABC. About Rs 45 crore, about 24 months from investment approval to commissioning. This workbook covers only the scope of the construction contractor.
Sheets | Assumptions: handover date and external delivery dates (scenario levers). L3 Reference: the 11 L3 activities given to the contractor. L4-L6 Schedule: the working schedule with logic, dates and actuals columns.
Level definitions | L3 = package activity in the consultant schedule (e.g. Civil Works - Process Buildings). L4 = facility / area work package (e.g. Waste Receiving & Tipping Hall). L5 = work group (e.g. Foundations). L6 = executable task reported daily by a supervisor (e.g. Excavate for footings).
Linkage key | The Activity ID (format GWP-<discipline>-<number>, e.g. GWP-CIV-1130) is the linkage point. Every L4-L6 row also carries its L3 Parent ID and immediate Parent ID, so a reported L6 task always resolves up to its L3/L4 node in P6.
Who does what | Contractor keeps L5/L6 (approved by consultant). Supervisors report L6 starts and finishes. The planning engineer confirms and updates P6. L4/L5 rows are never reported directly; they roll up.
Completion rule | A task is complete when the site team finishes the work. Inspection and testing are separate tasks in the last L3 node (Section GWP-L3-110), not part of the work task.
Rollup rules | Summary Planned/Actual Start = earliest child. Summary Actual Finish appears only when all L6 tasks below it are finished, then = latest child finish. Summary % Complete = L6 % complete weighted by planned duration. Status derives from the actual dates.
Schedule logic | L6 tasks use Finish-to-Start unless stated (some Start-to-Start with lag). Start = latest predecessor constraint, moved to next working day. Six-day week (Sunday off). Changing a duration or an external delivery offset recalculates all dates.
Legend | Yellow cells: fill in during demo (Actual Start, Actual Finish, % Complete, Remarks at L6 level; and delivery offsets on the Assumptions sheet). Blue text: hardcoded input (duration, quantity). Black: formula. Green: link to another sheet. Use the outline buttons (1/2/3) at the left of the schedule to collapse to L4, L5 or L6.
Assumptions | All durations, quantities, delivery lead times and logic are synthetic assumptions made for teaching realism, not taken from any real OIL project. Quantities are indicative and are meant to make daily reports look realistic (e.g. "poured 45 m3").
Example of a filled-in row | GWP-CIV-1250 ¦ Excavate for footings (Bldg B) ¦ Actual Start 18-Nov-27 ¦ Actual Finish 24-Nov-27 ¦ % Complete 100%. Only L6 rows are filled; the parent L5 and L4 rows and the L3 node update by formula. Delete any test entries before reuse.
Row counts (live)
L4 work packages | 19
L5 work groups | 40
L6 tasks (incl. 2 milestones) | 149
External milestones | 7
Total rows | 215

## Assumptions
Assumptions & Scenario Levers
Blue = editable input. All dates in the Schedule recalculate from these cells.
Item | Value | Basis
Investment approval date (case project) | 2027-01-01 | Case project assumption agreed with Sandip: ~24 months approval to commissioning
Site handover to construction contractor (start of scope) | 2027-10-04 | Assumption: ~9 months after approval for land, statutory clearances and design
Commissioning target (case project) | 2028-12-31 | Assumption: 24 months from approval
Working calendar | Mon-Sat (Sunday off) | Assumption: 6-day week, no public holidays or monsoon losses modelled
External / interface milestones (not contractor tasks - they drive the contractor schedule)
Milestone ID | Description | Offset (working days from handover) | Delivery date (calculated)
GWP-EXT-1010 | IFC structural steel drawings released by consultant | 20 | 2027-10-27
GWP-EXT-1020 | Trommel screen, conveyors, feed hopper & weighbridge delivered at site (supplier) | 145 | 2028-03-21
GWP-EXT-1030 | Shredder & baling press delivered at site (supplier) | 155 | 2028-04-01
GWP-EXT-1040 | Aeration blowers, compost turner & finishing screen delivered at site (supplier) | 150 | 2028-03-27
GWP-EXT-1050 | ETP skid, leachate & fire water pumps delivered at site (supplier) | 155 | 2028-04-01
GWP-EXT-1060 | Transformer, HT/LT panels & DG set delivered at site (owner-supplied) | 175 | 2028-04-25
GWP-EXT-1070 | PLC/SCADA panels & field instruments delivered at site (supplier) | 205 | 2028-05-30
Notes:
1. Offsets are illustrative assumptions (supplier/owner lead times after design and ordering). Change an offset to test how a late delivery pushes the contractor schedule.
2. Task durations, quantities and logic in the Schedule are synthetic, chosen for teaching realism; they are not from any real OIL project.
3. No holidays, monsoon or weather losses are modelled. Dates use WORKDAY.INTL with Sunday as the only non-working day.
Formulas:
Delivery date (calculated) = WORKDAY.INTL(Assumptions!$B6,[Basis],11)

## L4-L6 Schedule
Level 4-5-6 Schedule: Construction Contractor Scope - Urban Garbage Treatment Plant (100 TPD), Town XYZ, Company ABC
Synthetic teaching dataset. Link key = Activity ID (Primavera P6 style). Yellow cells = site inputs (Actual Start / Actual Finish / % Complete) at L6 task level; L4/L5 rows roll up automatically. Blue = editable input, black = formula.
Activity ID | WBS | Level | L3 Parent ID | Parent ID | Activity Name | Type | Discipline | Reporting Role | Qty | UoM | Orig Duration (wd) | Predecessors (FS unless stated) | Planned Start | Planned Finish | Leaf (Y/N) | Actual Start | Actual Finish | % Complete | Status | Remarks
GWP-EXT-1010 | - | EXT | - | - | IFC structural steel drawings released by consultant | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2027-10-27 | 2027-10-27 | N |  |  |  | -
GWP-EXT-1020 | - | EXT | - | - | Trommel screen, conveyors, feed hopper & weighbridge delivered at site (supplier) | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2028-03-21 | 2028-03-21 | N |  |  |  | -
GWP-EXT-1030 | - | EXT | - | - | Shredder & baling press delivered at site (supplier) | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2028-04-01 | 2028-04-01 | N |  |  |  | -
GWP-EXT-1040 | - | EXT | - | - | Aeration blowers, compost turner & finishing screen delivered at site (supplier) | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2028-03-27 | 2028-03-27 | N |  |  |  | -
GWP-EXT-1050 | - | EXT | - | - | ETP skid, leachate & fire water pumps delivered at site (supplier) | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2028-04-01 | 2028-04-01 | N |  |  |  | -
GWP-EXT-1060 | - | EXT | - | - | Transformer, HT/LT panels & DG set delivered at site (owner-supplied) | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2028-04-25 | 2028-04-25 | N |  |  |  | -
GWP-EXT-1070 | - | EXT | - | - | PLC/SCADA panels & field instruments delivered at site (supplier) | External milestone | EXT | Supplier / Owner / Consultant |  |  | 0 | Input date (Assumptions sheet) | 2028-05-30 | 2028-05-30 | N |  |  |  | -
GWP-GEN-1010 | GWP.C01.01 | L4 | GWP-L3-010 | GWP-L3-010 | Mobilisation & Temporary Facilities | Summary | GEN | Contractor Site Engineer |  |  | 14 |  | 2027-10-04 | 2027-10-19 | N |  |  | 0% | Not Started
GWP-GEN-1020 | GWP.C01.01.01 | L5 | GWP-L3-010 | GWP-GEN-1010 | Site Establishment | Summary | GEN | Contractor Site Engineer |  |  | 14 |  | 2027-10-04 | 2027-10-19 | N |  |  | 0% | Not Started
GWP-GEN-1030 | GWP.C01.01.01.01 | L6 | GWP-L3-010 | GWP-GEN-1020 | Site handover & joint survey with consultant | Task | GEN | Contractor Site Engineer | 1 | LS | 2 | Site handover date (Assumptions) | 2027-10-04 | 2027-10-05 | Y |  |  |  | Not Started
GWP-GEN-1040 | GWP.C01.01.01.02 | L6 | GWP-L3-010 | GWP-GEN-1020 | Set up site office, stores & storage yard | Task | GEN | Contractor Site Engineer | 1 | LS | 6 | GWP-GEN-1030 FS | 2027-10-06 | 2027-10-12 | Y |  |  |  | Not Started
GWP-GEN-1050 | GWP.C01.01.01.03 | L6 | GWP-L3-010 | GWP-GEN-1020 | Set up labour camp, canteen & sanitation | Task | GEN | Contractor Site Engineer | 1 | LS | 8 | GWP-GEN-1030 FS | 2027-10-06 | 2027-10-14 | Y |  |  |  | Not Started
GWP-GEN-1060 | GWP.C01.01.01.04 | L6 | GWP-L3-010 | GWP-GEN-1020 | Arrange temporary power (DG) & water supply | Task | GEN | Contractor Site Engineer | 1 | LS | 7 | GWP-GEN-1030 FS | 2027-10-06 | 2027-10-13 | Y |  |  |  | Not Started
GWP-GEN-1070 | GWP.C01.01.01.05 | L6 | GWP-L3-010 | GWP-GEN-1020 | Erect temporary fencing, signage & site gate | Task | GEN | Contractor Site Engineer | 300 | RM | 4 | GWP-GEN-1030 FS | 2027-10-06 | 2027-10-09 | Y |  |  |  | Not Started
GWP-GEN-1080 | GWP.C01.01.01.06 | L6 | GWP-L3-010 | GWP-GEN-1020 | Mobilise cranes, excavators & batching equipment | Task | GEN | Contractor Site Engineer | 1 | LS | 6 | GWP-GEN-1040 FS | 2027-10-13 | 2027-10-19 | Y |  |  |  | Not Started
GWP-GEN-1090 | GWP.C01.01.02 | L5 | GWP-L3-010 | GWP-GEN-1010 | Quality & HSE Setup | Summary | GEN | Contractor Site Engineer |  |  | 11 |  | 2027-10-06 | 2027-10-18 | N |  |  | 0% | Not Started
GWP-HSE-1010 | GWP.C01.01.02.01 | L6 | GWP-L3-010 | GWP-GEN-1090 | HSE plan approval & worker induction | Task | HSE | Contractor HSE Officer | 1 | LS | 5 | GWP-GEN-1040 FS | 2027-10-13 | 2027-10-18 | Y |  |  |  | Not Started
GWP-QAQC-1010 | GWP.C01.01.02.02 | L6 | GWP-L3-010 | GWP-GEN-1090 | Approval of QAP / Inspection & Test Plans | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 8 | GWP-GEN-1030 FS | 2027-10-06 | 2027-10-14 | Y |  |  |  | Not Started
GWP-GEN-1100 | GWP.C01.01.02.03 | L6 | GWP-L3-010 | GWP-GEN-1090 | Establish survey control points & benchmarks | Task | GEN | Contractor Site Engineer | 12 | Nos | 4 | GWP-GEN-1030 FS | 2027-10-06 | 2027-10-09 | Y |  |  |  | Not Started
GWP-QAQC-1020 | GWP.C01.01.02.04 | L6 | GWP-L3-010 | GWP-GEN-1090 | Set up site material testing lab | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 5 | GWP-GEN-1040 FS | 2027-10-13 | 2027-10-18 | Y |  |  |  | Not Started
GWP-CIV-1010 | GWP.C02.01 | L4 | GWP-L3-020 | GWP-L3-020 | Earthwork & Site Grading | Summary | CIV | Civil Supervisor |  |  | 56 |  | 2027-10-20 | 2027-12-23 | N |  |  | 0% | Not Started
GWP-CIV-1020 | GWP.C02.01.01 | L5 | GWP-L3-020 | GWP-CIV-1010 | Clearing & Grading | Summary | CIV | Civil Supervisor |  |  | 25 |  | 2027-10-20 | 2027-11-17 | N |  |  | 0% | Not Started
GWP-CIV-1030 | GWP.C02.01.01.01 | L6 | GWP-L3-020 | GWP-CIV-1020 | Clear & grub site vegetation and debris | Task | CIV | Civil Supervisor | 25000 | m2 | 6 | GWP-GEN-1100 FS; GWP-GEN-1080 FS | 2027-10-20 | 2027-10-26 | Y |  |  |  | Not Started
GWP-CIV-1040 | GWP.C02.01.01.02 | L6 | GWP-L3-020 | GWP-CIV-1020 | Cut & fill to formation level | Task | CIV | Civil Supervisor | 18000 | m3 | 14 | GWP-CIV-1030 FS | 2027-10-27 | 2027-11-11 | Y |  |  |  | Not Started
GWP-CIV-1050 | GWP.C02.01.01.03 | L6 | GWP-L3-020 | GWP-CIV-1020 | Compaction & field density tests on filled area | Task | CIV | Civil Supervisor | 25000 | m2 | 5 | GWP-CIV-1040 FS | 2027-11-12 | 2027-11-17 | Y |  |  |  | Not Started
GWP-CIV-1060 | GWP.C02.01.02 | L5 | GWP-L3-020 | GWP-CIV-1010 | Boundary Wall & Main Gate | Summary | CIV | Civil Supervisor |  |  | 50 |  | 2027-10-27 | 2027-12-23 | N |  |  | 0% | Not Started
GWP-CIV-1070 | GWP.C02.01.02.01 | L6 | GWP-L3-020 | GWP-CIV-1060 | Excavate boundary wall foundation trench | Task | CIV | Civil Supervisor | 1200 | RM | 8 | GWP-CIV-1030 FS | 2027-10-27 | 2027-11-04 | Y |  |  |  | Not Started
GWP-CIV-1080 | GWP.C02.01.02.02 | L6 | GWP-L3-020 | GWP-CIV-1060 | Lay PCC and footing for boundary wall | Task | CIV | Civil Supervisor | 1200 | RM | 10 | GWP-CIV-1070 FS | 2027-11-05 | 2027-11-16 | Y |  |  |  | Not Started
GWP-CIV-1090 | GWP.C02.01.02.03 | L6 | GWP-L3-020 | GWP-CIV-1060 | Brick masonry for boundary wall | Task | CIV | Civil Supervisor | 1200 | RM | 20 | GWP-CIV-1080 FS | 2027-11-17 | 2027-12-09 | Y |  |  |  | Not Started
GWP-CIV-1100 | GWP.C02.01.02.04 | L6 | GWP-L3-020 | GWP-CIV-1060 | Plaster & paint boundary wall | Task | CIV | Civil Supervisor | 1200 | RM | 12 | GWP-CIV-1090 FS | 2027-12-10 | 2027-12-23 | Y |  |  |  | Not Started
GWP-CIV-1110 | GWP.C02.01.02.05 | L6 | GWP-L3-020 | GWP-CIV-1060 | Install main gate & security cabin | Task | CIV | Civil Supervisor | 1 | LS | 6 | GWP-CIV-1090 FS | 2027-12-10 | 2027-12-16 | Y |  |  |  | Not Started
GWP-CIV-1120 | GWP.C02.02 | L4 | GWP-L3-020 | GWP-L3-020 | Roads & Drainage | Summary | CIV | Civil Supervisor |  |  | 141 |  | 2027-11-18 | 2028-04-29 | N |  |  | 0% | Not Started
GWP-CIV-1130 | GWP.C02.02.01 | L5 | GWP-L3-020 | GWP-CIV-1120 | Storm Water Drainage | Summary | CIV | Civil Supervisor |  |  | 38 |  | 2027-11-18 | 2027-12-31 | N |  |  | 0% | Not Started
GWP-CIV-1140 | GWP.C02.02.01.01 | L6 | GWP-L3-020 | GWP-CIV-1130 | Excavate storm drain trenches | Task | CIV | Civil Supervisor | 900 | RM | 10 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-29 | Y |  |  |  | Not Started
GWP-CIV-1150 | GWP.C02.02.01.02 | L6 | GWP-L3-020 | GWP-CIV-1130 | PCC bed for drains | Task | CIV | Civil Supervisor | 900 | RM | 6 | GWP-CIV-1140 FS | 2027-11-30 | 2027-12-06 | Y |  |  |  | Not Started
GWP-CIV-1160 | GWP.C02.02.01.03 | L6 | GWP-L3-020 | GWP-CIV-1130 | Construct drain side walls (masonry/RCC) | Task | CIV | Civil Supervisor | 900 | RM | 16 | GWP-CIV-1150 FS | 2027-12-07 | 2027-12-24 | Y |  |  |  | Not Started
GWP-CIV-1170 | GWP.C02.02.01.04 | L6 | GWP-L3-020 | GWP-CIV-1130 | Fix drain covers and gratings | Task | CIV | Civil Supervisor | 900 | RM | 6 | GWP-CIV-1160 FS | 2027-12-25 | 2027-12-31 | Y |  |  |  | Not Started
GWP-CIV-1180 | GWP.C02.02.02 | L5 | GWP-L3-020 | GWP-CIV-1120 | Internal Roads | Summary | CIV | Civil Supervisor |  |  | 141 |  | 2027-11-18 | 2028-04-29 | N |  |  | 0% | Not Started
GWP-CIV-1190 | GWP.C02.02.02.01 | L6 | GWP-L3-020 | GWP-CIV-1180 | Subgrade preparation for internal roads | Task | CIV | Civil Supervisor | 6000 | m2 | 8 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-26 | Y |  |  |  | Not Started
GWP-CIV-1200 | GWP.C02.02.02.02 | L6 | GWP-L3-020 | GWP-CIV-1180 | Lay granular sub-base (GSB) & WBM | Task | CIV | Civil Supervisor | 6000 | m2 | 10 | GWP-CIV-1190 FS; GWP-PIP-1110 FS | 2027-12-16 | 2027-12-27 | Y |  |  |  | Not Started
GWP-CIV-1210 | GWP.C02.02.02.03 | L6 | GWP-L3-020 | GWP-CIV-1180 | Lay final concrete pavement & kerbs | Task | CIV | Civil Supervisor | 6000 | m2 | 14 | GWP-CIV-1200 FS; GWP-MEC-1220 FS; GWP-CIV-1170 FS | 2028-04-11 | 2028-04-26 | Y |  |  |  | Not Started
GWP-CIV-1220 | GWP.C02.02.02.04 | L6 | GWP-L3-020 | GWP-CIV-1180 | Road marking & signage | Task | CIV | Civil Supervisor | 1 | LS | 3 | GWP-CIV-1210 FS | 2028-04-27 | 2028-04-29 | Y |  |  |  | Not Started
GWP-CIV-1230 | GWP.C03.01 | L4 | GWP-L3-030 | GWP-L3-030 | Waste Receiving & Tipping Hall (Bldg B) | Summary | CIV | Civil Supervisor |  |  | 50 |  | 2027-11-18 | 2028-01-14 | N |  |  | 0% | Not Started
GWP-CIV-1240 | GWP.C03.01.01 | L5 | GWP-L3-030 | GWP-CIV-1230 | Foundations | Summary | CIV | Civil Supervisor |  |  | 26 |  | 2027-11-18 | 2027-12-17 | N |  |  | 0% | Not Started
GWP-CIV-1250 | GWP.C03.01.01.01 | L6 | GWP-L3-030 | GWP-CIV-1240 | Excavate for footings | Task | CIV | Civil Supervisor | 2200 | m3 | 6 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-24 | Y |  |  |  | Not Started
GWP-CIV-1260 | GWP.C03.01.01.02 | L6 | GWP-L3-030 | GWP-CIV-1240 | Lay PCC below footings | Task | CIV | Civil Supervisor | 110 | m3 | 3 | GWP-CIV-1250 FS | 2027-11-25 | 2027-11-27 | Y |  |  |  | Not Started
GWP-CIV-1270 | GWP.C03.01.01.03 | L6 | GWP-L3-030 | GWP-CIV-1240 | Footing reinforcement & shuttering | Task | CIV | Civil Supervisor | 38 | MT | 8 | GWP-CIV-1260 FS | 2027-11-29 | 2027-12-07 | Y |  |  |  | Not Started
GWP-CIV-1280 | GWP.C03.01.01.04 | L6 | GWP-L3-030 | GWP-CIV-1240 | Footing concreting (M25) | Task | CIV | Civil Supervisor | 360 | m3 | 5 | GWP-CIV-1270 FS | 2027-12-08 | 2027-12-13 | Y |  |  |  | Not Started
GWP-CIV-1290 | GWP.C03.01.01.05 | L6 | GWP-L3-030 | GWP-CIV-1240 | Backfill & compaction around footings | Task | CIV | Civil Supervisor | 1400 | m3 | 4 | GWP-CIV-1280 FS | 2027-12-14 | 2027-12-17 | Y |  |  |  | Not Started
GWP-CIV-1300 | GWP.C03.01.02 | L5 | GWP-L3-030 | GWP-CIV-1230 | Tipping Pit & Hopper Walls | Summary | CIV | Civil Supervisor |  |  | 40 |  | 2027-11-18 | 2028-01-03 | N |  |  | 0% | Not Started
GWP-CIV-1310 | GWP.C03.01.02.01 | L6 | GWP-L3-030 | GWP-CIV-1300 | Excavate tipping pit with shoring | Task | CIV | Civil Supervisor | 1500 | m3 | 8 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-26 | Y |  |  |  | Not Started
GWP-CIV-1320 | GWP.C03.01.02.02 | L6 | GWP-L3-030 | GWP-CIV-1300 | Pit raft reinforcement & shuttering | Task | CIV | Civil Supervisor | 45 | MT | 6 | GWP-CIV-1310 FS | 2027-11-27 | 2027-12-03 | Y |  |  |  | Not Started
GWP-CIV-1330 | GWP.C03.01.02.03 | L6 | GWP-L3-030 | GWP-CIV-1300 | Pit raft concreting | Task | CIV | Civil Supervisor | 280 | m3 | 4 | GWP-CIV-1320 FS | 2027-12-04 | 2027-12-08 | Y |  |  |  | Not Started
GWP-CIV-1340 | GWP.C03.01.02.04 | L6 | GWP-L3-030 | GWP-CIV-1300 | Pit wall reinforcement & shuttering | Task | CIV | Civil Supervisor | 60 | MT | 10 | GWP-CIV-1330 FS | 2027-12-09 | 2027-12-20 | Y |  |  |  | Not Started
GWP-CIV-1350 | GWP.C03.01.02.05 | L6 | GWP-L3-030 | GWP-CIV-1300 | Pit wall concreting | Task | CIV | Civil Supervisor | 320 | m3 | 5 | GWP-CIV-1340 FS | 2027-12-21 | 2027-12-25 | Y |  |  |  | Not Started
GWP-CIV-1360 | GWP.C03.01.02.06 | L6 | GWP-L3-030 | GWP-CIV-1300 | Waterproofing & protective coating of pit | Task | CIV | Civil Supervisor | 1400 | m2 | 7 | GWP-CIV-1350 FS | 2027-12-27 | 2028-01-03 | Y |  |  |  | Not Started
GWP-CIV-1370 | GWP.C03.01.03 | L5 | GWP-L3-030 | GWP-CIV-1230 | Superstructure & Floors | Summary | CIV | Civil Supervisor |  |  | 24 |  | 2027-12-18 | 2028-01-14 | N |  |  | 0% | Not Started
GWP-CIV-1380 | GWP.C03.01.03.01 | L6 | GWP-L3-030 | GWP-CIV-1370 | Column reinforcement & shuttering | Task | CIV | Civil Supervisor | 42 | MT | 10 | GWP-CIV-1290 FS | 2027-12-18 | 2027-12-29 | Y |  |  |  | Not Started
GWP-CIV-1390 | GWP.C03.01.03.02 | L6 | GWP-L3-030 | GWP-CIV-1370 | Column concreting | Task | CIV | Civil Supervisor | 180 | m3 | 4 | GWP-CIV-1380 FS | 2027-12-30 | 2028-01-03 | Y |  |  |  | Not Started
GWP-CIV-1400 | GWP.C03.01.03.03 | L6 | GWP-L3-030 | GWP-CIV-1370 | Plinth beam & floor slab | Task | CIV | Civil Supervisor | 420 | m3 | 10 | GWP-CIV-1390 FS; GWP-CIV-1350 FS | 2028-01-04 | 2028-01-14 | Y |  |  |  | Not Started
GWP-CIV-1410 | GWP.C03.01.03.04 | L6 | GWP-L3-030 | GWP-CIV-1370 | Approach ramp & retaining wall | Task | CIV | Civil Supervisor | 260 | m3 | 8 | GWP-CIV-1350 FS | 2027-12-27 | 2028-01-04 | Y |  |  |  | Not Started
GWP-CIV-1420 | GWP.C03.02 | L4 | GWP-L3-030 | GWP-L3-030 | Segregation & Processing Building (Bldg C) | Summary | CIV | Civil Supervisor |  |  | 70 |  | 2027-11-18 | 2028-02-07 | N |  |  | 0% | Not Started
GWP-CIV-1430 | GWP.C03.02.01 | L5 | GWP-L3-030 | GWP-CIV-1420 | Foundations | Summary | CIV | Civil Supervisor |  |  | 33 |  | 2027-11-18 | 2027-12-25 | N |  |  | 0% | Not Started
GWP-CIV-1440 | GWP.C03.02.01.01 | L6 | GWP-L3-030 | GWP-CIV-1430 | Excavate for footings | Task | CIV | Civil Supervisor | 3100 | m3 | 8 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-26 | Y |  |  |  | Not Started
GWP-CIV-1450 | GWP.C03.02.01.02 | L6 | GWP-L3-030 | GWP-CIV-1430 | Lay PCC below footings | Task | CIV | Civil Supervisor | 150 | m3 | 4 | GWP-CIV-1440 FS | 2027-11-27 | 2027-12-01 | Y |  |  |  | Not Started
GWP-CIV-1460 | GWP.C03.02.01.03 | L6 | GWP-L3-030 | GWP-CIV-1430 | Footing reinforcement & shuttering | Task | CIV | Civil Supervisor | 55 | MT | 10 | GWP-CIV-1450 FS | 2027-12-02 | 2027-12-13 | Y |  |  |  | Not Started
GWP-CIV-1470 | GWP.C03.02.01.04 | L6 | GWP-L3-030 | GWP-CIV-1430 | Footing concreting (M25) | Task | CIV | Civil Supervisor | 520 | m3 | 6 | GWP-CIV-1460 FS | 2027-12-14 | 2027-12-20 | Y |  |  |  | Not Started
GWP-CIV-1480 | GWP.C03.02.01.05 | L6 | GWP-L3-030 | GWP-CIV-1430 | Backfill & compaction around footings | Task | CIV | Civil Supervisor | 2000 | m3 | 5 | GWP-CIV-1470 FS | 2027-12-21 | 2027-12-25 | Y |  |  |  | Not Started
GWP-CIV-1490 | GWP.C03.02.02 | L5 | GWP-L3-030 | GWP-CIV-1420 | Equipment Foundations & Pedestals | Summary | CIV | Civil Supervisor |  |  | 12 |  | 2027-12-27 | 2028-01-08 | N |  |  | 0% | Not Started
GWP-CIV-1500 | GWP.C03.02.02.01 | L6 | GWP-L3-030 | GWP-CIV-1490 | Trommel screen foundation with anchor bolts | Task | CIV | Civil Supervisor | 45 | m3 | 7 | GWP-CIV-1480 FS | 2027-12-27 | 2028-01-03 | Y |  |  |  | Not Started
GWP-CIV-1510 | GWP.C03.02.02.02 | L6 | GWP-L3-030 | GWP-CIV-1490 | Conveyor support pedestals | Task | CIV | Civil Supervisor | 60 | m3 | 8 | GWP-CIV-1480 FS | 2027-12-27 | 2028-01-04 | Y |  |  |  | Not Started
GWP-CIV-1520 | GWP.C03.02.02.03 | L6 | GWP-L3-030 | GWP-CIV-1490 | Shredder & baling press foundations with anchor bolts | Task | CIV | Civil Supervisor | 110 | m3 | 9 | GWP-CIV-1480 FS | 2027-12-27 | 2028-01-05 | Y |  |  |  | Not Started
GWP-CIV-1530 | GWP.C03.02.02.04 | L6 | GWP-L3-030 | GWP-CIV-1490 | Survey check of anchor bolts & foundation levels | Task | CIV | Civil Supervisor | 1 | LS | 3 | GWP-CIV-1500 FS; GWP-CIV-1510 FS; GWP-CIV-1520 FS | 2028-01-06 | 2028-01-08 | Y |  |  |  | Not Started
GWP-CIV-1540 | GWP.C03.02.03 | L5 | GWP-L3-030 | GWP-CIV-1420 | Superstructure & Floors | Summary | CIV | Civil Supervisor |  |  | 37 |  | 2027-12-27 | 2028-02-07 | N |  |  | 0% | Not Started
GWP-CIV-1550 | GWP.C03.02.03.01 | L6 | GWP-L3-030 | GWP-CIV-1540 | Column reinforcement & shuttering | Task | CIV | Civil Supervisor | 60 | MT | 10 | GWP-CIV-1480 FS | 2027-12-27 | 2028-01-06 | Y |  |  |  | Not Started
GWP-CIV-1560 | GWP.C03.02.03.02 | L6 | GWP-L3-030 | GWP-CIV-1540 | Column concreting | Task | CIV | Civil Supervisor | 260 | m3 | 5 | GWP-CIV-1550 FS | 2028-01-07 | 2028-01-12 | Y |  |  |  | Not Started
GWP-CIV-1570 | GWP.C03.02.03.03 | L6 | GWP-L3-030 | GWP-CIV-1540 | Plinth beam & floor slab | Task | CIV | Civil Supervisor | 700 | m3 | 10 | GWP-CIV-1560 FS | 2028-01-13 | 2028-01-24 | Y |  |  |  | Not Started
GWP-CIV-1580 | GWP.C03.02.03.04 | L6 | GWP-L3-030 | GWP-CIV-1540 | Brick infill masonry | Task | CIV | Civil Supervisor | 1800 | m2 | 12 | GWP-CIV-1570 FS | 2028-01-25 | 2028-02-07 | Y |  |  |  | Not Started
GWP-CIV-1590 | GWP.C04.01 | L4 | GWP-L3-040 | GWP-L3-040 | Composting Yard | Summary | CIV | Civil Supervisor |  |  | 38 |  | 2027-11-18 | 2027-12-31 | N |  |  | 0% | Not Started
GWP-CIV-1600 | GWP.C04.01.01 | L5 | GWP-L3-040 | GWP-CIV-1590 | Windrow Platform | Summary | CIV | Civil Supervisor |  |  | 38 |  | 2027-11-18 | 2027-12-31 | N |  |  | 0% | Not Started
GWP-CIV-1610 | GWP.C04.01.01.01 | L6 | GWP-L3-040 | GWP-CIV-1600 | Excavation & levelling for compost platform | Task | CIV | Civil Supervisor | 6000 | m2 | 6 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-24 | Y |  |  |  | Not Started
GWP-CIV-1620 | GWP.C04.01.01.02 | L6 | GWP-L3-040 | GWP-CIV-1600 | Sub-base & compaction | Task | CIV | Civil Supervisor | 6000 | m2 | 5 | GWP-CIV-1610 FS | 2027-11-25 | 2027-11-30 | Y |  |  |  | Not Started
GWP-CIV-1630 | GWP.C04.01.01.03 | L6 | GWP-L3-040 | GWP-CIV-1600 | PCC & waterproofing membrane | Task | CIV | Civil Supervisor | 6000 | m2 | 5 | GWP-CIV-1620 FS | 2027-12-01 | 2027-12-06 | Y |  |  |  | Not Started
GWP-CIV-1640 | GWP.C04.01.01.04 | L6 | GWP-L3-040 | GWP-CIV-1600 | Reinforced concrete platform slab (bay-wise) | Task | CIV | Civil Supervisor | 900 | m3 | 14 | GWP-CIV-1630 FS | 2027-12-07 | 2027-12-22 | Y |  |  |  | Not Started
GWP-CIV-1650 | GWP.C04.01.01.05 | L6 | GWP-L3-040 | GWP-CIV-1600 | Leachate collection channels & sump connection | Task | CIV | Civil Supervisor | 400 | RM | 8 | GWP-CIV-1640 SS+6 | 2027-12-14 | 2027-12-22 | Y |  |  |  | Not Started
GWP-CIV-1660 | GWP.C04.01.01.06 | L6 | GWP-L3-040 | GWP-CIV-1600 | Bay dividing walls | Task | CIV | Civil Supervisor | 320 | RM | 8 | GWP-CIV-1640 FS | 2027-12-23 | 2027-12-31 | Y |  |  |  | Not Started
GWP-CIV-1670 | GWP.C04.02 | L4 | GWP-L3-040 | GWP-L3-040 | RDF Storage Shed | Summary | CIV | Civil Supervisor |  |  | 27 |  | 2027-11-18 | 2027-12-18 | N |  |  | 0% | Not Started
GWP-CIV-1680 | GWP.C04.02.01 | L5 | GWP-L3-040 | GWP-CIV-1670 | Foundations & Floor | Summary | CIV | Civil Supervisor |  |  | 27 |  | 2027-11-18 | 2027-12-18 | N |  |  | 0% | Not Started
GWP-CIV-1690 | GWP.C04.02.01.01 | L6 | GWP-L3-040 | GWP-CIV-1680 | Footing excavation | Task | CIV | Civil Supervisor | 600 | m3 | 5 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-23 | Y |  |  |  | Not Started
GWP-CIV-1700 | GWP.C04.02.01.02 | L6 | GWP-L3-040 | GWP-CIV-1680 | Footing PCC, reinforcement & concreting | Task | CIV | Civil Supervisor | 90 | m3 | 9 | GWP-CIV-1690 FS | 2027-11-24 | 2027-12-03 | Y |  |  |  | Not Started
GWP-CIV-1710 | GWP.C04.02.01.03 | L6 | GWP-L3-040 | GWP-CIV-1680 | Shed floor slab | Task | CIV | Civil Supervisor | 240 | m3 | 8 | GWP-CIV-1700 FS | 2027-12-04 | 2027-12-13 | Y |  |  |  | Not Started
GWP-CIV-1720 | GWP.C04.02.01.04 | L6 | GWP-L3-040 | GWP-CIV-1680 | Loading dock & ramp | Task | CIV | Civil Supervisor | 60 | m3 | 5 | GWP-CIV-1710 FS | 2027-12-14 | 2027-12-18 | Y |  |  |  | Not Started
GWP-CIV-1730 | GWP.C04.03 | L4 | GWP-L3-040 | GWP-L3-040 | Leachate Collection & Treatment Civil | Summary | CIV | Civil Supervisor |  |  | 29 |  | 2027-11-18 | 2027-12-21 | N |  |  | 0% | Not Started
GWP-CIV-1740 | GWP.C04.03.01 | L5 | GWP-L3-040 | GWP-CIV-1730 | Sump & Tanks | Summary | CIV | Civil Supervisor |  |  | 29 |  | 2027-11-18 | 2027-12-21 | N |  |  | 0% | Not Started
GWP-CIV-1750 | GWP.C04.03.01.01 | L6 | GWP-L3-040 | GWP-CIV-1740 | Excavate for leachate sump & equalisation tank | Task | CIV | Civil Supervisor | 450 | m3 | 6 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-24 | Y |  |  |  | Not Started
GWP-CIV-1760 | GWP.C04.03.01.02 | L6 | GWP-L3-040 | GWP-CIV-1740 | Tank raft reinforcement & concreting | Task | CIV | Civil Supervisor | 70 | m3 | 6 | GWP-CIV-1750 FS | 2027-11-25 | 2027-12-01 | Y |  |  |  | Not Started
GWP-CIV-1770 | GWP.C04.03.01.03 | L6 | GWP-L3-040 | GWP-CIV-1740 | Tank walls reinforcement & concreting | Task | CIV | Civil Supervisor | 110 | m3 | 10 | GWP-CIV-1760 FS | 2027-12-02 | 2027-12-13 | Y |  |  |  | Not Started
GWP-CIV-1780 | GWP.C04.03.01.04 | L6 | GWP-L3-040 | GWP-CIV-1740 | Water-tightness (fill) test & waterproofing | Task | CIV | Civil Supervisor | 1 | LS | 7 | GWP-CIV-1770 FS | 2027-12-14 | 2027-12-21 | Y |  |  |  | Not Started
GWP-CIV-1790 | GWP.C05.01 | L4 | GWP-L3-050 | GWP-L3-050 | Administration & Control Building | Summary | CIV | Civil Supervisor |  |  | 74 |  | 2027-11-18 | 2028-02-11 | N |  |  | 0% | Not Started
GWP-CIV-1800 | GWP.C05.01.01 | L5 | GWP-L3-050 | GWP-CIV-1790 | Structure | Summary | CIV | Civil Supervisor |  |  | 44 |  | 2027-11-18 | 2028-01-07 | N |  |  | 0% | Not Started
GWP-CIV-1810 | GWP.C05.01.01.01 | L6 | GWP-L3-050 | GWP-CIV-1800 | Excavation for foundations | Task | CIV | Civil Supervisor | 300 | m3 | 4 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-22 | Y |  |  |  | Not Started
GWP-CIV-1820 | GWP.C05.01.01.02 | L6 | GWP-L3-050 | GWP-CIV-1800 | Footing PCC, reinforcement & concreting | Task | CIV | Civil Supervisor | 60 | m3 | 8 | GWP-CIV-1810 FS | 2027-11-23 | 2027-12-01 | Y |  |  |  | Not Started
GWP-CIV-1830 | GWP.C05.01.01.03 | L6 | GWP-L3-050 | GWP-CIV-1800 | Columns, beams & slab (RCC frame) | Task | CIV | Civil Supervisor | 210 | m3 | 20 | GWP-CIV-1820 FS | 2027-12-02 | 2027-12-24 | Y |  |  |  | Not Started
GWP-CIV-1840 | GWP.C05.01.01.04 | L6 | GWP-L3-050 | GWP-CIV-1800 | Brick masonry & lintels | Task | CIV | Civil Supervisor | 850 | m2 | 12 | GWP-CIV-1830 FS | 2027-12-25 | 2028-01-07 | Y |  |  |  | Not Started
GWP-CIV-1850 | GWP.C05.01.02 | L5 | GWP-L3-050 | GWP-CIV-1790 | Finishing | Summary | CIV | Civil Supervisor |  |  | 30 |  | 2028-01-08 | 2028-02-11 | N |  |  | 0% | Not Started
GWP-CIV-1860 | GWP.C05.01.02.01 | L6 | GWP-L3-050 | GWP-CIV-1850 | Plastering (internal & external) | Task | CIV | Civil Supervisor | 1700 | m2 | 12 | GWP-CIV-1840 FS | 2028-01-08 | 2028-01-21 | Y |  |  |  | Not Started
GWP-CIV-1870 | GWP.C05.01.02.02 | L6 | GWP-L3-050 | GWP-CIV-1850 | Flooring & tiling | Task | CIV | Civil Supervisor | 650 | m2 | 10 | GWP-CIV-1860 FS | 2028-01-22 | 2028-02-02 | Y |  |  |  | Not Started
GWP-CIV-1880 | GWP.C05.01.02.03 | L6 | GWP-L3-050 | GWP-CIV-1850 | Doors, windows & glazing | Task | CIV | Civil Supervisor | 45 | Nos | 7 | GWP-CIV-1840 FS | 2028-01-08 | 2028-01-15 | Y |  |  |  | Not Started
GWP-CIV-1890 | GWP.C05.01.02.04 | L6 | GWP-L3-050 | GWP-CIV-1850 | Painting & final finishing | Task | CIV | Civil Supervisor | 1700 | m2 | 8 | GWP-CIV-1870 FS; GWP-CIV-1880 FS | 2028-02-03 | 2028-02-11 | Y |  |  |  | Not Started
GWP-CIV-1900 | GWP.C05.02 | L4 | GWP-L3-050 | GWP-L3-050 | Utility Structures | Summary | CIV | Civil Supervisor |  |  | 34 |  | 2027-11-18 | 2027-12-27 | N |  |  | 0% | Not Started
GWP-CIV-1910 | GWP.C05.02.01 | L5 | GWP-L3-050 | GWP-CIV-1900 | Substation, Fire Water & Weighbridge Civil | Summary | CIV | Civil Supervisor |  |  | 34 |  | 2027-11-18 | 2027-12-27 | N |  |  | 0% | Not Started
GWP-CIV-1920 | GWP.C05.02.01.01 | L6 | GWP-L3-050 | GWP-CIV-1910 | Electrical substation & DG room civil works | Task | CIV | Civil Supervisor | 1 | LS | 22 | GWP-CIV-1050 FS | 2027-11-18 | 2027-12-13 | Y |  |  |  | Not Started
GWP-CIV-1930 | GWP.C05.02.01.02 | L6 | GWP-L3-050 | GWP-CIV-1910 | Fire water tank & pump house civil works | Task | CIV | Civil Supervisor | 1 | LS | 25 | GWP-CIV-1050 FS | 2027-11-18 | 2027-12-16 | Y |  |  |  | Not Started
GWP-CIV-1940 | GWP.C05.02.01.03 | L6 | GWP-L3-050 | GWP-CIV-1910 | Weighbridge foundation & approach | Task | CIV | Civil Supervisor | 60 | m3 | 8 | GWP-CIV-1050 FS | 2027-11-18 | 2027-11-26 | Y |  |  |  | Not Started
GWP-CIV-1950 | GWP.C05.02.01.04 | L6 | GWP-L3-050 | GWP-CIV-1910 | Cable trench & duct bank civil works | Task | CIV | Civil Supervisor | 450 | RM | 12 | GWP-CIV-1920 FS | 2027-12-14 | 2027-12-27 | Y |  |  |  | Not Started
GWP-STR-1010 | GWP.C06.01 | L4 | GWP-L3-060 | GWP-L3-060 | Steel Structure - Processing Buildings | Summary | STR | Structural Supervisor |  |  | 110 |  | 2027-10-28 | 2028-03-03 | N |  |  | 0% | Not Started
GWP-STR-1020 | GWP.C06.01.01 | L5 | GWP-L3-060 | GWP-STR-1010 | Procurement & Fabrication | Summary | STR | Structural Supervisor |  |  | 41 |  | 2027-10-28 | 2027-12-14 | N |  |  | 0% | Not Started
GWP-STR-1030 | GWP.C06.01.01.01 | L6 | GWP-L3-060 | GWP-STR-1020 | Procure steel sections & plates (contractor scope) | Task | STR | Structural Supervisor | 240 | MT | 15 | GWP-EXT-1010 FS | 2027-10-28 | 2027-11-13 | Y |  |  |  | Not Started
GWP-STR-1040 | GWP.C06.01.01.02 | L6 | GWP-L3-060 | GWP-STR-1020 | Fabricate columns & roof trusses - Bldg B | Task | STR | Structural Supervisor | 85 | MT | 18 | GWP-STR-1030 FS | 2027-11-15 | 2027-12-04 | Y |  |  |  | Not Started
GWP-STR-1050 | GWP.C06.01.01.03 | L6 | GWP-L3-060 | GWP-STR-1020 | Fabricate trusses, crane girders & platforms - Bldg C | Task | STR | Structural Supervisor | 140 | MT | 22 | GWP-STR-1030 FS | 2027-11-15 | 2027-12-09 | Y |  |  |  | Not Started
GWP-STR-1060 | GWP.C06.01.01.04 | L6 | GWP-L3-060 | GWP-STR-1020 | Shot-blast & primer coat | Task | STR | Structural Supervisor | 225 | MT | 8 | GWP-STR-1040 FS | 2027-12-06 | 2027-12-14 | Y |  |  |  | Not Started
GWP-STR-1070 | GWP.C06.01.02 | L5 | GWP-L3-060 | GWP-STR-1010 | Erection - Bldg B (Tipping Hall) | Summary | STR | Structural Supervisor |  |  | 28 |  | 2028-01-04 | 2028-02-04 | N |  |  | 0% | Not Started
GWP-STR-1080 | GWP.C06.01.02.01 | L6 | GWP-L3-060 | GWP-STR-1070 | Erect steel columns & bracings | Task | STR | Structural Supervisor | 85 | MT | 8 | GWP-STR-1060 FS; GWP-CIV-1390 FS | 2028-01-04 | 2028-01-12 | Y |  |  |  | Not Started
GWP-STR-1090 | GWP.C06.01.02.02 | L6 | GWP-L3-060 | GWP-STR-1070 | Erect roof trusses & purlins | Task | STR | Structural Supervisor | 85 | MT | 10 | GWP-STR-1080 FS | 2028-01-13 | 2028-01-24 | Y |  |  |  | Not Started
GWP-STR-1100 | GWP.C06.01.02.03 | L6 | GWP-L3-060 | GWP-STR-1070 | Fix roof sheeting & rainwater gutters | Task | STR | Structural Supervisor | 2400 | m2 | 10 | GWP-STR-1090 FS | 2028-01-25 | 2028-02-04 | Y |  |  |  | Not Started
GWP-STR-1110 | GWP.C06.01.02.04 | L6 | GWP-L3-060 | GWP-STR-1070 | Bolt torque check & alignment survey | Task | STR | Structural Supervisor | 1 | LS | 3 | GWP-STR-1090 FS | 2028-01-25 | 2028-01-27 | Y |  |  |  | Not Started
GWP-STR-1120 | GWP.C06.01.03 | L5 | GWP-L3-060 | GWP-STR-1010 | Erection - Bldg C (Processing Building) | Summary | STR | Structural Supervisor |  |  | 34 |  | 2028-01-13 | 2028-02-21 | N |  |  | 0% | Not Started
GWP-STR-1130 | GWP.C06.01.03.01 | L6 | GWP-L3-060 | GWP-STR-1120 | Erect steel columns & bracings | Task | STR | Structural Supervisor | 140 | MT | 10 | GWP-STR-1050 FS; GWP-STR-1060 FS; GWP-CIV-1560 FS | 2028-01-13 | 2028-01-24 | Y |  |  |  | Not Started
GWP-STR-1140 | GWP.C06.01.03.02 | L6 | GWP-L3-060 | GWP-STR-1120 | Erect crane girders & mezzanine framing | Task | STR | Structural Supervisor | 50 | MT | 10 | GWP-STR-1130 FS | 2028-01-25 | 2028-02-04 | Y |  |  |  | Not Started
GWP-STR-1150 | GWP.C06.01.03.03 | L6 | GWP-L3-060 | GWP-STR-1120 | Erect roof trusses & purlins | Task | STR | Structural Supervisor | 60 | MT | 12 | GWP-STR-1130 FS | 2028-01-25 | 2028-02-07 | Y |  |  |  | Not Started
GWP-STR-1160 | GWP.C06.01.03.04 | L6 | GWP-L3-060 | GWP-STR-1120 | Fix roof sheeting & rainwater gutters | Task | STR | Structural Supervisor | 3200 | m2 | 12 | GWP-STR-1150 FS | 2028-02-08 | 2028-02-21 | Y |  |  |  | Not Started
GWP-STR-1170 | GWP.C06.01.03.05 | L6 | GWP-L3-060 | GWP-STR-1120 | Erect sorting platforms, staircases & handrails | Task | STR | Structural Supervisor | 30 | MT | 12 | GWP-STR-1140 FS | 2028-02-05 | 2028-02-18 | Y |  |  |  | Not Started
GWP-STR-1180 | GWP.C06.01.04 | L5 | GWP-L3-060 | GWP-STR-1010 | Paint & Touch-up | Summary | STR | Structural Supervisor |  |  | 10 |  | 2028-02-22 | 2028-03-03 | N |  |  | 0% | Not Started
GWP-STR-1190 | GWP.C06.01.04.01 | L6 | GWP-L3-060 | GWP-STR-1180 | Final coat painting & touch-up | Task | STR | Structural Supervisor | 5600 | m2 | 10 | GWP-STR-1100 FS; GWP-STR-1160 FS; GWP-STR-1170 FS | 2028-02-22 | 2028-03-03 | Y |  |  |  | Not Started
GWP-STR-1200 | GWP.C06.02 | L4 | GWP-L3-060 | GWP-L3-060 | Steel Structure - RDF Shed | Summary | STR | Structural Supervisor |  |  | 31 |  | 2027-11-15 | 2027-12-20 | N |  |  | 0% | Not Started
GWP-STR-1210 | GWP.C06.02.01 | L5 | GWP-L3-060 | GWP-STR-1200 | RDF Shed Steel | Summary | STR | Structural Supervisor |  |  | 31 |  | 2027-11-15 | 2027-12-20 | N |  |  | 0% | Not Started
GWP-STR-1220 | GWP.C06.02.01.01 | L6 | GWP-L3-060 | GWP-STR-1210 | Fabricate RDF shed steel | Task | STR | Structural Supervisor | 45 | MT | 12 | GWP-STR-1030 FS | 2027-11-15 | 2027-11-27 | Y |  |  |  | Not Started
GWP-STR-1230 | GWP.C06.02.01.02 | L6 | GWP-L3-060 | GWP-STR-1210 | Erect RDF shed frame & roof sheeting | Task | STR | Structural Supervisor | 1500 | m2 | 14 | GWP-STR-1220 FS; GWP-CIV-1700 FS | 2027-12-04 | 2027-12-20 | Y |  |  |  | Not Started
GWP-MEC-1010 | GWP.C07.01 | L4 | GWP-L3-070 | GWP-L3-070 | Processing Line Equipment | Summary | MEC | Mechanical Supervisor |  |  | 22 |  | 2028-03-22 | 2028-04-15 | N |  |  | 0% | Not Started
GWP-MEC-1020 | GWP.C07.01.01 | L5 | GWP-L3-070 | GWP-MEC-1010 | Trommel & Conveyor System | Summary | MEC | Mechanical Supervisor |  |  | 22 |  | 2028-03-22 | 2028-04-15 | N |  |  | 0% | Not Started
GWP-MEC-1030 | GWP.C07.01.01.01 | L6 | GWP-L3-070 | GWP-MEC-1020 | Position & level trommel screen on foundation | Task | MEC | Mechanical Supervisor | 1 | Nos | 6 | GWP-EXT-1020 FS; GWP-CIV-1530 FS | 2028-03-22 | 2028-03-28 | Y |  |  |  | Not Started
GWP-MEC-1040 | GWP.C07.01.01.02 | L6 | GWP-L3-070 | GWP-MEC-1020 | Alignment, grouting & anchor bolt tightening - trommel | Task | MEC | Mechanical Supervisor | 1 | Nos | 4 | GWP-MEC-1030 FS | 2028-03-29 | 2028-04-01 | Y |  |  |  | Not Started
GWP-MEC-1050 | GWP.C07.01.01.03 | L6 | GWP-L3-070 | GWP-MEC-1020 | Erect belt conveyor frames & idlers | Task | MEC | Mechanical Supervisor | 9 | Nos | 14 | GWP-EXT-1020 FS; GWP-CIV-1510 FS; GWP-STR-1170 FS | 2028-03-22 | 2028-04-06 | Y |  |  |  | Not Started
GWP-MEC-1060 | GWP.C07.01.01.04 | L6 | GWP-L3-070 | GWP-MEC-1020 | Install conveyor belts, drives & guards | Task | MEC | Mechanical Supervisor | 9 | Nos | 8 | GWP-MEC-1050 FS | 2028-04-07 | 2028-04-15 | Y |  |  |  | Not Started
GWP-MEC-1070 | GWP.C07.01.01.05 | L6 | GWP-L3-070 | GWP-MEC-1020 | Install magnetic & eddy current separators | Task | MEC | Mechanical Supervisor | 2 | Nos | 5 | GWP-MEC-1060 SS+3 | 2028-04-11 | 2028-04-15 | Y |  |  |  | Not Started
GWP-MEC-1080 | GWP.C07.01.02 | L5 | GWP-L3-070 | GWP-MEC-1010 | Shredding & Baling | Summary | MEC | Mechanical Supervisor |  |  | 10 |  | 2028-04-03 | 2028-04-13 | N |  |  | 0% | Not Started
GWP-MEC-1090 | GWP.C07.01.02.01 | L6 | GWP-L3-070 | GWP-MEC-1080 | Position & align shredder | Task | MEC | Mechanical Supervisor | 1 | Nos | 7 | GWP-EXT-1030 FS; GWP-CIV-1530 FS | 2028-04-03 | 2028-04-10 | Y |  |  |  | Not Started
GWP-MEC-1100 | GWP.C07.01.02.02 | L6 | GWP-L3-070 | GWP-MEC-1080 | Grout & tighten anchor bolts - shredder | Task | MEC | Mechanical Supervisor | 1 | Nos | 3 | GWP-MEC-1090 FS | 2028-04-11 | 2028-04-13 | Y |  |  |  | Not Started
GWP-MEC-1110 | GWP.C07.01.02.03 | L6 | GWP-L3-070 | GWP-MEC-1080 | Position & align baling press | Task | MEC | Mechanical Supervisor | 1 | Nos | 6 | GWP-EXT-1030 FS; GWP-CIV-1530 FS | 2028-04-03 | 2028-04-08 | Y |  |  |  | Not Started
GWP-MEC-1120 | GWP.C07.01.02.04 | L6 | GWP-L3-070 | GWP-MEC-1080 | Connect hydraulic power pack & tubing | Task | MEC | Mechanical Supervisor | 1 | Nos | 4 | GWP-MEC-1110 FS | 2028-04-10 | 2028-04-13 | Y |  |  |  | Not Started
GWP-MEC-1130 | GWP.C07.02 | L4 | GWP-L3-070 | GWP-L3-070 | Composting & Handling Equipment | Summary | MEC | Mechanical Supervisor |  |  | 17 |  | 2028-03-22 | 2028-04-10 | N |  |  | 0% | Not Started
GWP-MEC-1140 | GWP.C07.02.01 | L5 | GWP-L3-070 | GWP-MEC-1130 | Aeration & Turning | Summary | MEC | Mechanical Supervisor |  |  | 10 |  | 2028-03-28 | 2028-04-07 | N |  |  | 0% | Not Started
GWP-MEC-1150 | GWP.C07.02.01.01 | L6 | GWP-L3-070 | GWP-MEC-1140 | Install aeration blowers & air headers | Task | MEC | Mechanical Supervisor | 4 | Nos | 10 | GWP-EXT-1040 FS; GWP-CIV-1640 FS | 2028-03-28 | 2028-04-07 | Y |  |  |  | Not Started
GWP-MEC-1160 | GWP.C07.02.01.02 | L6 | GWP-L3-070 | GWP-MEC-1140 | Assemble compost turner | Task | MEC | Mechanical Supervisor | 1 | Nos | 5 | GWP-EXT-1040 FS; GWP-CIV-1660 FS | 2028-03-28 | 2028-04-01 | Y |  |  |  | Not Started
GWP-MEC-1170 | GWP.C07.02.01.03 | L6 | GWP-L3-070 | GWP-MEC-1140 | Install compost finishing screen & bagging unit | Task | MEC | Mechanical Supervisor | 1 | Nos | 8 | GWP-EXT-1040 FS; GWP-CIV-1660 FS | 2028-03-28 | 2028-04-05 | Y |  |  |  | Not Started
GWP-MEC-1180 | GWP.C07.02.02 | L5 | GWP-L3-070 | GWP-MEC-1130 | Weighbridge & Hopper Equipment | Summary | MEC | Mechanical Supervisor |  |  | 17 |  | 2028-03-22 | 2028-04-10 | N |  |  | 0% | Not Started
GWP-MEC-1190 | GWP.C07.02.02.01 | L6 | GWP-L3-070 | GWP-MEC-1180 | Erect weighbridge platform & load cells | Task | MEC | Mechanical Supervisor | 1 | Nos | 8 | GWP-CIV-1940 FS; GWP-EXT-1020 FS | 2028-03-22 | 2028-03-30 | Y |  |  |  | Not Started
GWP-MEC-1200 | GWP.C07.02.02.02 | L6 | GWP-L3-070 | GWP-MEC-1180 | Install feed hopper & apron feeder | Task | MEC | Mechanical Supervisor | 1 | Nos | 8 | GWP-EXT-1020 FS; GWP-CIV-1400 FS | 2028-03-22 | 2028-03-30 | Y |  |  |  | Not Started
GWP-MEC-1210 | GWP.C07.02.02.03 | L6 | GWP-L3-070 | GWP-MEC-1180 | Install overhead grab crane in tipping hall | Task | MEC | Mechanical Supervisor | 1 | Nos | 12 | GWP-STR-1090 FS; GWP-EXT-1020 FS | 2028-03-22 | 2028-04-04 | Y |  |  |  | Not Started
GWP-MEC-1220 | GWP.C07.02.02.04 | L6 | GWP-L3-070 | GWP-MEC-1180 | Heavy equipment lifting & placement complete | Milestone | MEC | Mechanical Supervisor |  |  | 0 | GWP-MEC-1030 FS; GWP-MEC-1090 FS; GWP-MEC-1110 FS; GWP-MEC-1210 FS | 2028-04-10 | 2028-04-10 | Y |  |  |  | Not Started
GWP-PIP-1010 | GWP.C08.01 | L4 | GWP-L3-080 | GWP-L3-080 | Leachate Treatment Plant (ETP) Mechanical | Summary | PIP | Piping Supervisor |  |  | 163 |  | 2027-10-28 | 2028-05-04 | N |  |  | 0% | Not Started
GWP-PIP-1020 | GWP.C08.01.01 | L5 | GWP-L3-080 | GWP-PIP-1010 | Equipment & Pumps | Summary | PIP | Piping Supervisor |  |  | 6 |  | 2028-04-03 | 2028-04-08 | N |  |  | 0% | Not Started
GWP-PIP-1030 | GWP.C08.01.01.01 | L6 | GWP-L3-080 | GWP-PIP-1020 | Place ETP skid & dosing tanks | Task | PIP | Piping Supervisor | 1 | Nos | 5 | GWP-EXT-1050 FS; GWP-CIV-1780 FS | 2028-04-03 | 2028-04-07 | Y |  |  |  | Not Started
GWP-PIP-1040 | GWP.C08.01.01.02 | L6 | GWP-L3-080 | GWP-PIP-1020 | Install leachate & transfer pumps | Task | PIP | Piping Supervisor | 4 | Nos | 6 | GWP-EXT-1050 FS; GWP-CIV-1780 FS | 2028-04-03 | 2028-04-08 | Y |  |  |  | Not Started
GWP-PIP-1050 | GWP.C08.01.02 | L5 | GWP-L3-080 | GWP-PIP-1010 | Piping | Summary | PIP | Piping Supervisor |  |  | 163 |  | 2027-10-28 | 2028-05-04 | N |  |  | 0% | Not Started
GWP-PIP-1060 | GWP.C08.01.02.01 | L6 | GWP-L3-080 | GWP-PIP-1050 | Prefabricate pipe spools (leachate & process water) | Task | PIP | Piping Supervisor | 180 | Spools | 12 | GWP-EXT-1010 FS | 2027-10-28 | 2027-11-10 | Y |  |  |  | Not Started
GWP-PIP-1070 | GWP.C08.01.02.02 | L6 | GWP-L3-080 | GWP-PIP-1050 | Erect pipe spools & supports | Task | PIP | Piping Supervisor | 180 | Spools | 14 | GWP-PIP-1060 FS; GWP-PIP-1040 FS; GWP-PIP-1030 FS | 2028-04-10 | 2028-04-25 | Y |  |  |  | Not Started
GWP-PIP-1080 | GWP.C08.01.02.03 | L6 | GWP-L3-080 | GWP-PIP-1050 | Complete field welds & NDT (RT/DP) | Task | PIP | Piping Supervisor | 220 | Joints | 8 | GWP-PIP-1070 FS | 2028-04-26 | 2028-05-04 | Y |  |  |  | Not Started
GWP-PIP-1090 | GWP.C08.02 | L4 | GWP-L3-080 | GWP-L3-080 | Fire Water & Utility Piping | Summary | PIP | Piping Supervisor |  |  | 117 |  | 2027-11-27 | 2028-04-11 | N |  |  | 0% | Not Started
GWP-PIP-1100 | GWP.C08.02.01 | L5 | GWP-L3-080 | GWP-PIP-1090 | Fire Water Network | Summary | PIP | Piping Supervisor |  |  | 117 |  | 2027-11-27 | 2028-04-11 | N |  |  | 0% | Not Started
GWP-PIP-1110 | GWP.C08.02.01.01 | L6 | GWP-L3-080 | GWP-PIP-1100 | Lay underground fire water main | Task | PIP | Piping Supervisor | 900 | RM | 16 | GWP-CIV-1190 FS | 2027-11-27 | 2027-12-15 | Y |  |  |  | Not Started
GWP-PIP-1120 | GWP.C08.02.01.02 | L6 | GWP-L3-080 | GWP-PIP-1100 | Erect hydrants, monitors & sprinkler headers | Task | PIP | Piping Supervisor | 24 | Nos | 12 | GWP-PIP-1110 FS; GWP-STR-1160 FS | 2028-02-22 | 2028-03-06 | Y |  |  |  | Not Started
GWP-PIP-1130 | GWP.C08.02.01.03 | L6 | GWP-L3-080 | GWP-PIP-1100 | Install fire pumps & jockey pump | Task | PIP | Piping Supervisor | 3 | Nos | 8 | GWP-CIV-1930 FS; GWP-EXT-1050 FS | 2028-04-03 | 2028-04-11 | Y |  |  |  | Not Started
GWP-PIP-1140 | GWP.C08.02.02 | L5 | GWP-L3-080 | GWP-PIP-1090 | Water Supply & Drainage | Summary | PIP | Piping Supervisor |  |  | 10 |  | 2028-01-08 | 2028-01-19 | N |  |  | 0% | Not Started
GWP-PIP-1150 | GWP.C08.02.02.01 | L6 | GWP-L3-080 | GWP-PIP-1140 | Domestic water supply & plumbing (admin building) | Task | PIP | Piping Supervisor | 1 | LS | 10 | GWP-CIV-1840 FS | 2028-01-08 | 2028-01-19 | Y |  |  |  | Not Started
GWP-PIP-1160 | GWP.C08.02.02.02 | L6 | GWP-L3-080 | GWP-PIP-1140 | Sewer line & septic tank connection | Task | PIP | Piping Supervisor | 1 | LS | 8 | GWP-CIV-1840 FS | 2028-01-08 | 2028-01-17 | Y |  |  |  | Not Started
GWP-ELE-1010 | GWP.C09.01 | L4 | GWP-L3-090 | GWP-L3-090 | Power Distribution | Summary | ELE | Electrical Supervisor |  |  | 176 |  | 2027-11-27 | 2028-06-19 | N |  |  | 0% | Not Started
GWP-ELE-1020 | GWP.C09.01.01 | L5 | GWP-L3-090 | GWP-ELE-1010 | Substation, DG & Earthing | Summary | ELE | Electrical Supervisor |  |  | 139 |  | 2027-11-27 | 2028-05-06 | N |  |  | 0% | Not Started
GWP-ELE-1030 | GWP.C09.01.01.01 | L6 | GWP-L3-090 | GWP-ELE-1020 | Install 11kV/415V transformer & HT panel | Task | ELE | Electrical Supervisor | 1 | Nos | 8 | GWP-EXT-1060 FS; GWP-CIV-1920 FS | 2028-04-26 | 2028-05-04 | Y |  |  |  | Not Started
GWP-ELE-1040 | GWP.C09.01.01.02 | L6 | GWP-L3-090 | GWP-ELE-1020 | Install LT panels, MCCs & capacitor bank | Task | ELE | Electrical Supervisor | 8 | Nos | 10 | GWP-EXT-1060 FS; GWP-CIV-1920 FS | 2028-04-26 | 2028-05-06 | Y |  |  |  | Not Started
GWP-ELE-1050 | GWP.C09.01.01.03 | L6 | GWP-L3-090 | GWP-ELE-1020 | Install DG set & AMF panel | Task | ELE | Electrical Supervisor | 1 | Nos | 6 | GWP-EXT-1060 FS; GWP-CIV-1920 FS | 2028-04-26 | 2028-05-02 | Y |  |  |  | Not Started
GWP-ELE-1060 | GWP.C09.01.01.04 | L6 | GWP-L3-090 | GWP-ELE-1020 | Earthing grid & lightning protection installation | Task | ELE | Electrical Supervisor | 1 | LS | 14 | GWP-CIV-1190 FS | 2027-11-27 | 2027-12-13 | Y |  |  |  | Not Started
GWP-ELE-1070 | GWP.C09.01.02 | L5 | GWP-L3-090 | GWP-ELE-1010 | Cabling | Summary | ELE | Electrical Supervisor |  |  | 97 |  | 2028-02-22 | 2028-06-13 | N |  |  | 0% | Not Started
GWP-ELE-1080 | GWP.C09.01.02.01 | L6 | GWP-L3-090 | GWP-ELE-1070 | Erect cable trays & supports | Task | ELE | Electrical Supervisor | 3500 | RM | 15 | GWP-STR-1160 FS; GWP-CIV-1950 FS | 2028-02-22 | 2028-03-09 | Y |  |  |  | Not Started
GWP-ELE-1090 | GWP.C09.01.02.02 | L6 | GWP-L3-090 | GWP-ELE-1070 | Lay power & control cables in trays and trenches | Task | ELE | Electrical Supervisor | 18000 | RM | 18 | GWP-ELE-1080 FS; GWP-ELE-1040 FS | 2028-05-08 | 2028-05-27 | Y |  |  |  | Not Started
GWP-ELE-1100 | GWP.C09.01.02.03 | L6 | GWP-L3-090 | GWP-ELE-1070 | Cable dressing, glanding & termination | Task | ELE | Electrical Supervisor | 420 | Nos | 14 | GWP-ELE-1090 FS; GWP-MEC-1220 FS; GWP-MEC-1060 FS | 2028-05-29 | 2028-06-13 | Y |  |  |  | Not Started
GWP-ELE-1110 | GWP.C09.01.03 | L5 | GWP-L3-090 | GWP-ELE-1010 | Lighting & Equipment Earthing | Summary | ELE | Electrical Supervisor |  |  | 102 |  | 2028-02-22 | 2028-06-19 | N |  |  | 0% | Not Started
GWP-ELE-1120 | GWP.C09.01.03.01 | L6 | GWP-L3-090 | GWP-ELE-1110 | Install internal lighting & small power in buildings | Task | ELE | Electrical Supervisor | 1 | LS | 14 | GWP-CIV-1860 FS; GWP-STR-1160 FS | 2028-02-22 | 2028-03-08 | Y |  |  |  | Not Started
GWP-ELE-1130 | GWP.C09.01.03.02 | L6 | GWP-L3-090 | GWP-ELE-1110 | Install high-mast & street lighting | Task | ELE | Electrical Supervisor | 28 | Nos | 10 | GWP-CIV-1210 FS | 2028-04-27 | 2028-05-08 | Y |  |  |  | Not Started
GWP-ELE-1140 | GWP.C09.01.03.03 | L6 | GWP-L3-090 | GWP-ELE-1110 | Connect equipment earthing & test earth pits | Task | ELE | Electrical Supervisor | 40 | Nos | 5 | GWP-ELE-1100 FS | 2028-06-14 | 2028-06-19 | Y |  |  |  | Not Started
GWP-INS-1010 | GWP.C10.01 | L4 | GWP-L3-100 | GWP-L3-100 | Instrumentation & Automation | Summary | INS | Instrumentation Supervisor |  |  | 107 |  | 2028-02-22 | 2028-06-24 | N |  |  | 0% | Not Started
GWP-INS-1020 | GWP.C10.01.01 | L5 | GWP-L3-100 | GWP-INS-1010 | Field Instruments | Summary | INS | Instrumentation Supervisor |  |  | 102 |  | 2028-02-28 | 2028-06-24 | N |  |  | 0% | Not Started
GWP-INS-1030 | GWP.C10.01.01.01 | L6 | GWP-L3-100 | GWP-INS-1020 | Install instrument cable trays & conduits | Task | INS | Instrumentation Supervisor | 2200 | RM | 10 | GWP-ELE-1080 SS+5 | 2028-02-28 | 2028-03-09 | Y |  |  |  | Not Started
GWP-INS-1040 | GWP.C10.01.01.02 | L6 | GWP-L3-100 | GWP-INS-1020 | Mount field instruments (level, pressure, flow, proximity) | Task | INS | Instrumentation Supervisor | 110 | Nos | 10 | GWP-EXT-1070 FS; GWP-MEC-1060 FS | 2028-05-31 | 2028-06-10 | Y |  |  |  | Not Started
GWP-INS-1050 | GWP.C10.01.01.03 | L6 | GWP-L3-100 | GWP-INS-1020 | Lay & terminate instrument cables | Task | INS | Instrumentation Supervisor | 9000 | RM | 12 | GWP-INS-1030 FS; GWP-INS-1040 FS | 2028-06-12 | 2028-06-24 | Y |  |  |  | Not Started
GWP-INS-1060 | GWP.C10.01.02 | L5 | GWP-L3-100 | GWP-INS-1010 | Control System | Summary | INS | Instrumentation Supervisor |  |  | 98 |  | 2028-02-22 | 2028-06-14 | N |  |  | 0% | Not Started
GWP-INS-1070 | GWP.C10.01.02.01 | L6 | GWP-L3-100 | GWP-INS-1060 | Install PLC/SCADA panels & control room furniture | Task | INS | Instrumentation Supervisor | 4 | Nos | 8 | GWP-EXT-1070 FS; GWP-CIV-1890 FS | 2028-05-31 | 2028-06-08 | Y |  |  |  | Not Started
GWP-INS-1080 | GWP.C10.01.02.02 | L6 | GWP-L3-100 | GWP-INS-1060 | Weighbridge indicator & software integration wiring | Task | INS | Instrumentation Supervisor | 1 | Nos | 5 | GWP-MEC-1190 FS; GWP-INS-1070 FS | 2028-06-09 | 2028-06-14 | Y |  |  |  | Not Started
GWP-INS-1090 | GWP.C10.01.02.03 | L6 | GWP-L3-100 | GWP-INS-1060 | Install CCTV, fire alarm & PA system | Task | INS | Instrumentation Supervisor | 1 | LS | 10 | GWP-CIV-1890 FS; GWP-STR-1160 FS | 2028-02-22 | 2028-03-03 | Y |  |  |  | Not Started
GWP-QAQC-1030 | GWP.C11.01 | L4 | GWP-L3-110 | GWP-L3-110 | Inspection, Testing & Mechanical Completion | Summary | QAQC | Contractor QA/QC Engineer |  |  | 119 |  | 2028-03-04 | 2028-07-20 | N |  |  | 0% | Not Started
GWP-QAQC-1040 | GWP.C11.01.01 | L5 | GWP-L3-110 | GWP-QAQC-1030 | Civil & Structural Inspection | Summary | QAQC | Contractor QA/QC Engineer |  |  | 55 |  | 2028-03-04 | 2028-05-06 | N |  |  | 0% | Not Started
GWP-QAQC-1050 | GWP.C11.01.01.01 | L6 | GWP-L3-110 | GWP-QAQC-1040 | Civil works final inspection & as-built survey | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 6 | GWP-CIV-1890 FS; GWP-CIV-1220 FS; GWP-CIV-1780 FS; GWP-CIV-1650 FS; GWP-CIV-1720 FS; GWP-CIV-1100 FS; GWP-CIV-1110 FS; GWP-CIV-1170 FS | 2028-05-01 | 2028-05-06 | Y |  |  |  | Not Started
GWP-QAQC-1060 | GWP.C11.01.01.02 | L6 | GWP-L3-110 | GWP-QAQC-1040 | Structural steel final inspection & bolt torque audit | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 4 | GWP-STR-1190 FS; GWP-STR-1230 FS | 2028-03-04 | 2028-03-08 | Y |  |  |  | Not Started
GWP-QAQC-1070 | GWP.C11.01.02 | L5 | GWP-L3-110 | GWP-QAQC-1030 | Mechanical & Piping Tests | Summary | QAQC | Contractor QA/QC Engineer |  |  | 45 |  | 2028-05-05 | 2028-06-26 | N |  |  | 0% | Not Started
GWP-QAQC-1080 | GWP.C11.01.02.01 | L6 | GWP-L3-110 | GWP-QAQC-1070 | Hydrotest of piping and leachate tanks | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 5 | GWP-PIP-1080 FS; GWP-PIP-1120 FS | 2028-05-05 | 2028-05-10 | Y |  |  |  | Not Started
GWP-QAQC-1090 | GWP.C11.01.02.02 | L6 | GWP-L3-110 | GWP-QAQC-1070 | Flushing, cleaning & leak test | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 3 | GWP-QAQC-1080 FS | 2028-05-11 | 2028-05-13 | Y |  |  |  | Not Started
GWP-QAQC-1100 | GWP.C11.01.02.03 | L6 | GWP-L3-110 | GWP-QAQC-1070 | Final alignment & no-load (cold) run of machines | Task | QAQC | Contractor QA/QC Engineer | 14 | Nos | 6 | GWP-ELE-1140 FS; GWP-MEC-1040 FS; GWP-MEC-1070 FS; GWP-MEC-1100 FS; GWP-MEC-1120 FS; GWP-MEC-1150 FS; GWP-MEC-1160 FS; GWP-MEC-1170 FS; GWP-MEC-1200 FS; GWP-MEC-1210 FS | 2028-06-20 | 2028-06-26 | Y |  |  |  | Not Started
GWP-QAQC-1110 | GWP.C11.01.03 | L5 | GWP-L3-110 | GWP-QAQC-1030 | Electrical & Instrument Tests | Summary | QAQC | Contractor QA/QC Engineer |  |  | 18 |  | 2028-06-14 | 2028-07-04 | N |  |  | 0% | Not Started
GWP-QAQC-1120 | GWP.C11.01.03.01 | L6 | GWP-L3-110 | GWP-QAQC-1110 | Megger insulation test of cables & motors | Task | QAQC | Contractor QA/QC Engineer | 420 | Nos | 5 | GWP-ELE-1100 FS | 2028-06-14 | 2028-06-19 | Y |  |  |  | Not Started
GWP-QAQC-1130 | GWP.C11.01.03.02 | L6 | GWP-L3-110 | GWP-QAQC-1110 | Relay & protection settings test, panel energisation | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 4 | GWP-QAQC-1120 FS; GWP-ELE-1030 FS; GWP-ELE-1050 FS | 2028-06-20 | 2028-06-23 | Y |  |  |  | Not Started
GWP-QAQC-1140 | GWP.C11.01.03.03 | L6 | GWP-L3-110 | GWP-QAQC-1110 | Instrument loop checks & calibration | Task | QAQC | Contractor QA/QC Engineer | 110 | Loops | 8 | GWP-INS-1050 FS; GWP-INS-1070 FS; GWP-INS-1080 FS | 2028-06-26 | 2028-07-04 | Y |  |  |  | Not Started
GWP-QAQC-1150 | GWP.C11.01.04 | L5 | GWP-L3-110 | GWP-QAQC-1030 | Punch List & Handover | Summary | QAQC | Contractor QA/QC Engineer |  |  | 14 |  | 2028-07-05 | 2028-07-20 | N |  |  | 0% | Not Started
GWP-QAQC-1160 | GWP.C11.01.04.01 | L6 | GWP-L3-110 | GWP-QAQC-1150 | Punch list walkdown & rectification | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 12 | GWP-QAQC-1100 FS; GWP-QAQC-1130 FS; GWP-QAQC-1140 FS; GWP-QAQC-1090 FS; GWP-QAQC-1050 FS; GWP-QAQC-1060 FS; GWP-ELE-1120 FS; GWP-ELE-1130 FS; GWP-INS-1090 FS; GWP-MEC-1190 FS | 2028-07-05 | 2028-07-18 | Y |  |  |  | Not Started
GWP-QAQC-1170 | GWP.C11.01.04.02 | L6 | GWP-L3-110 | GWP-QAQC-1150 | Compile as-built drawings & test records dossier | Task | QAQC | Contractor QA/QC Engineer | 1 | LS | 10 | GWP-QAQC-1160 SS+4 | 2028-07-10 | 2028-07-20 | Y |  |  |  | Not Started
GWP-QAQC-1180 | GWP.C11.01.04.03 | L6 | GWP-L3-110 | GWP-QAQC-1150 | Mechanical Completion certificate (construction package) | Milestone | QAQC | Contractor QA/QC Engineer |  |  | 0 | GWP-QAQC-1160 FS; GWP-QAQC-1170 FS | 2028-07-20 | 2028-07-20 | Y |  |  |  | Not Started
Formulas:
Planned Start = MIN([Planned Start, row below]:N25)
Planned Start = IF([Orig Duration (wd)]=0,[Planned Finish, row above],WORKDAY.INTL([Planned Finish, row above],1,11))
Planned Finish = [Planned Start]
Planned Finish = MAX([Planned Finish, row below]:O25)
Orig Duration (wd) = NETWORKDAYS.INTL([Planned Start],[Planned Finish],11)

## L3 Reference
Level 3 Activities Assigned to the Construction Contractor (Consultant P6 schedule)
Dates, counts and progress are calculated from the L4-L6 Schedule sheet. In the full project these L3 nodes sit inside the consultant's P6 L3 schedule.
L3 Activity ID | WBS | L3 Activity Name | Scope Summary | Planned Start | Planned Finish | Duration (wd) | # L4 | # L5 | # L6 tasks | Actual Start | Actual Finish | % Complete | Status
GWP-L3-010 | GWP.C01 | Site Mobilisation & Temporary Facilities | Site handover, temporary facilities, HSE/QA setup, survey control | 2027-10-04 | 2027-10-19 | 14 | 1 | 2 | 10 |  |  | 0% | Not Started
GWP-L3-020 | GWP.C02 | Site Development & Enabling Works | Grading, boundary wall, storm drains, internal roads | 2027-10-20 | 2028-04-29 | 166 | 2 | 4 | 16 |  |  | 0% | Not Started
GWP-L3-030 | GWP.C03 | Civil Works - Process Buildings | Tipping/receiving hall (Bldg B) and segregation & processing building (Bldg C): foundations, RCC, floors | 2027-11-18 | 2028-02-07 | 70 | 2 | 6 | 28 |  |  | 0% | Not Started
GWP-L3-040 | GWP.C04 | Civil Works - Composting Yard, RDF Shed & Leachate Tanks | Compost platform, RDF shed foundation/floor, leachate sump and tanks | 2027-11-18 | 2027-12-31 | 38 | 3 | 3 | 14 |  |  | 0% | Not Started
GWP-L3-050 | GWP.C05 | Civil Works - Administration & Utility Buildings | Admin/control building, substation & DG room, fire water tank, weighbridge foundation | 2027-11-18 | 2028-02-11 | 74 | 2 | 3 | 12 |  |  | 0% | Not Started
GWP-L3-060 | GWP.C06 | Structural Steel Fabrication & Erection | Trusses, columns, crane girders, platforms, roof sheeting, painting | 2027-10-28 | 2028-03-03 | 110 | 2 | 5 | 16 |  |  | 0% | Not Started
GWP-L3-070 | GWP.C07 | Mechanical Equipment Erection | Erection and alignment of supplier-furnished process equipment | 2028-03-22 | 2028-04-15 | 22 | 2 | 4 | 16 |  |  | 0% | Not Started
GWP-L3-080 | GWP.C08 | Piping, Fire Water & ETP Mechanical Works | Leachate/process piping, fire water network, ETP skids and pumps, plumbing | 2027-10-28 | 2028-05-04 | 163 | 2 | 4 | 10 |  |  | 0% | Not Started
GWP-L3-090 | GWP.C09 | Electrical Installation | Transformer, panels, DG, earthing, cable trays, cabling, lighting | 2027-11-27 | 2028-06-19 | 176 | 1 | 3 | 10 |  |  | 0% | Not Started
GWP-L3-100 | GWP.C10 | Instrumentation & Automation Installation | Field instruments, PLC/SCADA, weighbridge integration, CCTV & fire alarm | 2028-02-22 | 2028-06-24 | 107 | 1 | 2 | 6 |  |  | 0% | Not Started
GWP-L3-110 | GWP.C11 | Construction Inspection, Testing & Mechanical Completion | Hydrotests, megger, loop checks, cold runs, punch list, documentation, MC certificate | 2028-03-04 | 2028-07-20 | 119 | 1 | 4 | 11 |  |  | 0% | Not Started
|  | Package total |  | 2027-10-04 | 2028-07-20 | 250 | 19 | 40 | 149
The last L3 node (Inspection, Testing & Mechanical Completion) ends with milestone "Mechanical Completion certificate (construction package)"; pre-commissioning and commissioning follow in other packages of the full L3 schedule.
Formulas:
Planned Start = MINIFS('L4-[Actual Finish, row below] Schedule'!$N6:N220,'L4-[Actual Finish, row below] Schedule'!$D6:D220,[L3 Activity ID])
Planned Start = MINIFS('L4-[Actual Finish] Schedule'!$N6:N220,'L4-[Actual Finish] Schedule'!$D6:D220,[L3 Activity ID])
Planned Finish = MAXIFS('L4-[Actual Finish, row below] Schedule'!$O6:O220,'L4-[Actual Finish, row below] Schedule'!$D6:D220,[L3 Activity ID])
Planned Finish = MAXIFS('L4-[Actual Finish] Schedule'!$O6:O220,'L4-[Actual Finish] Schedule'!$D6:D220,[L3 Activity ID])
Duration (wd) = NETWORKDAYS.INTL([Planned Start],[Planned Finish],11)