## README
L3 Schedule (Synthetic Case)
Purpose | The consultant-level (L3) schedule for the case project, from investment approval to commissioning. It shows where the construction contractor's L4-L6 schedule sits in the whole project and gives the students the parent activities to which field updates roll up.
Sheets | L3 Schedule: activities, logic, dates and a monthly bar chart. Key Dates: milestones and consistency checks. This README.
Phases | 1 Project Initiation, Approval & Land; 2 Statutory Clearances & Inspections; 3 Utility Arrangements; 4 Design & Engineering; 5 Procurement; 6 Equipment Manufacture, Inspection & Delivery; 7 Construction (Contractor Package); 8 Completion, Pre-commissioning & Commissioning.
Activity IDs | Format GWP-L3-nnn. The 11 contractor L3 activities are GWP-L3-010 to GWP-L3-110 and match the L4-L6 Schedule workbook. Other packages use the hundreds digit: 2xx approval and land, 3xx statutory, 4xx utilities, 5xx design, 6xx procurement, 8xx supplier manufacture and delivery, 9xx completion and commissioning. Phase rows are GWP-PH-n.
Link to L4-L6 workbook | Contractor rows (green bars) carry fixed start and finish dates copied from the L4-L6 Schedule workbook. Site handover (GWP-L3-000) is driven by contract award and statutory logic and lands on the handover date that workbook assumes. The Key Dates sheet checks this.
Back-solved durations | Durations of GWP-L3-530, 640 and the equipment manufacture rows (810 to 860) were set so that structural steel IFC release, contract signing and supplier deliveries land on the dates assumed in the L4-L6 workbook. They are illustrative.
Logic and calendar | Finish-to-Start unless stated, with a few Start-to-Start lags. Six-day week (Sunday off), no holidays. Total float is not calculated. Durations and logic are synthetic assumptions for teaching, not from any real project.
Legend | Blue text: hardcoded input. Black: formula. Green text: link to another sheet. Yellow fill: key input to change. Bar colours: navy = phase, blue = L3 activity, green = contractor fixed window, red = milestone.
Result | Approval on 1 Jan 2027; site handover 4 Oct 2027; Mechanical Completion 20 Jul 2028; commissioning acceptance 22 Dec 2028, about one week before the 31 Dec 2028 target. See Key Dates.

## L3 Schedule
Level 3 Schedule: Urban Garbage Treatment Plant (100 TPD), Town XYZ, Company ABC - Investment Approval to Commissioning
Synthetic teaching schedule in Primavera P6 style. Blue = input, black = formula. Contractor L3 windows (green) are fixed from the L4-L6 Schedule workbook. Six-day week (Sunday off).
Activity ID | WBS | Level | Activity Name | Type | Responsible | Orig Duration (wd) | Predecessors (FS unless stated) | Planned Start | Planned Finish | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01
GWP-PH-1 | GWP.01 | Phase | Project Initiation, Approval & Land Acquisition |  |  | 106 |  | 2027-01-01 | 2027-05-04
GWP-L3-200 | GWP.01.01 | L3 | Investment approval by Company ABC Board | Milestone | Company ABC | 0 | Board decision date (input) | 2027-01-01 | 2027-01-01
GWP-L3-210 | GWP.01.02 | L3 | Appoint project management consultant (PMC) | Task | Company ABC | 40 | GWP-L3-200 FS | 2027-01-02 | 2027-02-17
GWP-L3-220 | GWP.01.03 | L3 | Project organisation, budget & baseline schedule approval | Task | Company ABC | 20 | GWP-L3-210 FS | 2027-02-18 | 2027-03-12
GWP-L3-230 | GWP.01.04 | L3 | Identify and finalise land parcel | Task | Company ABC | 20 | GWP-L3-200 FS | 2027-01-02 | 2027-01-25
GWP-L3-240 | GWP.01.05 | L3 | Land title verification & due diligence | Task | Company ABC | 15 | GWP-L3-230 FS | 2027-01-26 | 2027-02-11
GWP-L3-250 | GWP.01.06 | L3 | Land transfer / lease agreement with municipality | Task | Company ABC | 25 | GWP-L3-240 FS | 2027-02-12 | 2027-03-12
GWP-L3-260 | GWP.01.07 | L3 | Land registration & mutation | Task | Company ABC | 15 | GWP-L3-250 FS | 2027-03-13 | 2027-03-30
GWP-L3-270 | GWP.01.08 | L3 | Land possession & boundary demarcation | Task | Company ABC | 5 | GWP-L3-260 FS | 2027-03-31 | 2027-04-05
GWP-L3-275 | GWP.01.09 | L3 | Topographic survey | Task | PMC / Consultant | 10 | GWP-L3-270 FS | 2027-04-06 | 2027-04-16
GWP-L3-280 | GWP.01.10 | L3 | Geotechnical investigation & soil report | Task | PMC / Consultant | 25 | GWP-L3-270 FS | 2027-04-06 | 2027-05-04
GWP-PH-2 | GWP.02 | Phase | Statutory Clearances & Inspections |  |  | 515 |  | 2027-01-02 | 2028-08-24
GWP-L3-300 | GWP.02.01 | L3 | Prepare statutory application documents (site details, process description) | Task | PMC / Consultant | 30 | GWP-L3-200 FS | 2027-01-02 | 2027-02-05
GWP-L3-310 | GWP.02.02 | L3 | Land use / zoning permission (Town Planning) | Task | Company ABC | 45 | GWP-L3-250 FS; GWP-L3-300 FS | 2027-03-13 | 2027-05-04
GWP-L3-320 | GWP.02.03 | L3 | Consent to Establish (State Pollution Control Board) | Task | Company ABC | 60 | GWP-L3-310 FS | 2027-05-05 | 2027-07-13
GWP-L3-330 | GWP.02.04 | L3 | Building plan approval (Town Planning Authority) | Task | Company ABC | 40 | GWP-L3-510 FS | 2027-05-22 | 2027-07-07
GWP-L3-340 | GWP.02.05 | L3 | Groundwater / borewell NOC | Task | Company ABC | 30 | GWP-L3-310 FS | 2027-05-05 | 2027-06-08
GWP-L3-350 | GWP.02.06 | L3 | Electrical drawings approval & power sanction (Electrical Inspectorate) | Task | Company ABC | 35 | GWP-L3-550 FS | 2027-05-22 | 2027-07-01
GWP-L3-360 | GWP.02.07 | L3 | Fire safety provisional NOC | Task | Company ABC | 30 | GWP-L3-330 FS | 2027-07-08 | 2027-08-11
GWP-L3-370 | GWP.02.08 | L3 | Labour licence & BOCW registration for construction | Task | Contractor | 10 | GWP-L3-630 FS | 2027-09-16 | 2027-09-27
GWP-L3-380 | GWP.02.09 | L3 | Consent to Operate application & inspection (SPCB) | Task | Company ABC | 30 | GWP-L3-900 FS | 2028-07-21 | 2028-08-24
GWP-L3-385 | GWP.02.10 | L3 | Electrical Inspector approval for energisation | Task | Company ABC | 25 | GWP-L3-090 FS | 2028-06-20 | 2028-07-18
GWP-L3-390 | GWP.02.11 | L3 | Final fire safety NOC (inspection) | Task | Company ABC | 25 | GWP-L3-080 FS | 2028-05-05 | 2028-06-02
GWP-PH-3 | GWP.03 | Phase | Utility Arrangements |  |  | 160 |  | 2027-03-13 | 2027-09-15
GWP-L3-400 | GWP.03.01 | L3 | Power: load sanction application to DISCOM | Task | Company ABC | 20 | GWP-L3-250 FS | 2027-03-13 | 2027-04-05
GWP-L3-410 | GWP.03.02 | L3 | Power: DISCOM estimate & payment | Task | Company ABC | 20 | GWP-L3-400 FS | 2027-04-06 | 2027-04-28
GWP-L3-420 | GWP.03.03 | L3 | Power: 11 kV line, metering & HT connection by DISCOM | Task | DISCOM | 100 | GWP-L3-410 FS | 2027-04-29 | 2027-08-23
GWP-L3-430 | GWP.03.04 | L3 | Water: source permission from municipal water board | Task | Company ABC | 30 | GWP-L3-250 FS | 2027-03-13 | 2027-04-16
GWP-L3-440 | GWP.03.05 | L3 | Water: pipeline connection to site | Task | Municipality | 45 | GWP-L3-430 FS | 2027-04-17 | 2027-06-08
GWP-L3-450 | GWP.03.06 | L3 | Approach road & site access improvement | Task | Municipality | 40 | GWP-L3-270 FS | 2027-04-06 | 2027-05-21
GWP-L3-460 | GWP.03.07 | L3 | Feedstock supply agreement with municipality (waste quantity, tipping fee) | Task | Company ABC | 60 | GWP-L3-220 FS | 2027-03-13 | 2027-05-21
GWP-L3-470 | GWP.03.08 | L3 | Treated water / storm discharge point permission | Task | Company ABC | 25 | GWP-L3-310 FS | 2027-05-05 | 2027-06-02
GWP-L3-480 | GWP.03.09 | L3 | Telecom & internet connectivity for SCADA | Task | Company ABC | 20 | GWP-L3-420 FS | 2027-08-24 | 2027-09-15
GWP-PH-4 | GWP.04 | Phase | Design & Engineering |  |  | 216 |  | 2027-02-18 | 2027-10-27
GWP-L3-500 | GWP.04.01 | L3 | Basic engineering: process flow, mass balance & P&IDs | Task | PMC / Consultant | 40 | GWP-L3-210 FS | 2027-02-18 | 2027-04-05
GWP-L3-510 | GWP.04.02 | L3 | Plot plan & general arrangement of buildings | Task | PMC / Consultant | 30 | GWP-L3-500 FS; GWP-L3-275 FS | 2027-04-17 | 2027-05-21
GWP-L3-520 | GWP.04.03 | L3 | Civil & structural design: foundations & RCC (IFC) | Task | PMC / Consultant | 60 | GWP-L3-510 FS; GWP-L3-280 FS | 2027-05-22 | 2027-07-30
GWP-L3-530 | GWP.04.04 | L3 | Structural steel design, fabrication drawings & IFC release (incl. shop drawing approval) | Task | PMC / Consultant | 76 | GWP-L3-520 FS | 2027-07-31 | 2027-10-27
GWP-L3-540 | GWP.04.05 | L3 | Mechanical equipment specifications & datasheets | Task | PMC / Consultant | 25 | GWP-L3-500 FS | 2027-04-06 | 2027-05-04
GWP-L3-550 | GWP.04.06 | L3 | Electrical design (single line diagram, load list, layouts) | Task | PMC / Consultant | 40 | GWP-L3-500 FS | 2027-04-06 | 2027-05-21
GWP-L3-560 | GWP.04.07 | L3 | Instrumentation & control design (I/O list, PLC architecture) | Task | PMC / Consultant | 40 | GWP-L3-500 FS | 2027-04-06 | 2027-05-21
GWP-L3-570 | GWP.04.08 | L3 | Piping, ETP & fire water design and isometrics | Task | PMC / Consultant | 45 | GWP-L3-500 FS; GWP-L3-540 FS | 2027-05-05 | 2027-06-25
GWP-L3-580 | GWP.04.09 | L3 | HAZOP / safety review & design freeze | Task | PMC / Consultant | 10 | GWP-L3-570 FS; GWP-L3-550 FS; GWP-L3-560 FS | 2027-06-26 | 2027-07-07
GWP-L3-590 | GWP.04.10 | L3 | Vendor drawing review & approval (foundation loads, anchor details) | Task | PMC / Consultant | 40 | GWP-L3-660 FS | 2027-07-31 | 2027-09-15
GWP-PH-5 | GWP.05 | Phase | Procurement |  |  | 130 |  | 2027-05-05 | 2027-10-02
GWP-L3-600 | GWP.05.01 | L3 | Tender documents & BOQ for construction contract | Task | PMC / Consultant | 30 | GWP-L3-510 FS | 2027-05-22 | 2027-06-25
GWP-L3-610 | GWP.05.02 | L3 | Tender floating, pre-bid meeting & bid submission | Task | Company ABC | 35 | GWP-L3-600 FS | 2027-06-26 | 2027-08-05
GWP-L3-620 | GWP.05.03 | L3 | Technical & commercial evaluation | Task | Company ABC | 20 | GWP-L3-610 FS | 2027-08-06 | 2027-08-28
GWP-L3-630 | GWP.05.04 | L3 | Negotiation, approval & Letter of Award (LOA) | Task | Company ABC | 15 | GWP-L3-620 FS | 2027-08-30 | 2027-09-15
GWP-L3-640 | GWP.05.05 | L3 | Contract signing, performance guarantee & mobilisation advance | Task | Company ABC | 15 | GWP-L3-630 FS | 2027-09-16 | 2027-10-02
GWP-L3-650 | GWP.05.06 | L3 | Process equipment: tender & evaluation (trommel, conveyors, shredder, baler) | Task | Company ABC | 60 | GWP-L3-540 FS | 2027-05-05 | 2027-07-13
GWP-L3-660 | GWP.05.07 | L3 | Process equipment: negotiation & purchase order | Task | Company ABC | 15 | GWP-L3-650 FS | 2027-07-14 | 2027-07-30
GWP-L3-670 | GWP.05.08 | L3 | Composting equipment: tender, evaluation & purchase order | Task | Company ABC | 75 | GWP-L3-540 FS | 2027-05-05 | 2027-07-30
GWP-L3-680 | GWP.05.09 | L3 | ETP skid & pumps: tender, evaluation & purchase order | Task | Company ABC | 75 | GWP-L3-570 FS | 2027-06-26 | 2027-09-21
GWP-L3-690 | GWP.05.10 | L3 | Electrical equipment (transformer, HT/LT panels, DG): tender, evaluation & PO | Task | Company ABC | 90 | GWP-L3-550 FS | 2027-05-22 | 2027-09-03
GWP-L3-695 | GWP.05.11 | L3 | PLC/SCADA & instruments: tender, evaluation & PO | Task | Company ABC | 75 | GWP-L3-560 FS | 2027-05-22 | 2027-08-17
GWP-PH-6 | GWP.06 | Phase | Equipment Manufacture, Inspection & Delivery |  |  | 261 |  | 2027-07-31 | 2028-05-30
GWP-L3-810 | GWP.06.01 | L3 | Manufacture & factory inspection (FAT): Trommel, conveyors, feed hopper & weighbridge | Task | Supplier | 189 | GWP-L3-660 FS | 2027-07-31 | 2028-03-07
GWP-L3-815 | GWP.06.02 | L3 | Dispatch & delivery at site: Trommel, conveyors, feed hopper & weighbridge | Task | Supplier | 12 | GWP-L3-810 FS | 2028-03-08 | 2028-03-21
GWP-L3-820 | GWP.06.03 | L3 | Manufacture & factory inspection (FAT): Shredder & baling press | Task | Supplier | 199 | GWP-L3-660 FS | 2027-07-31 | 2028-03-18
GWP-L3-825 | GWP.06.04 | L3 | Dispatch & delivery at site: Shredder & baling press | Task | Supplier | 12 | GWP-L3-820 FS | 2028-03-20 | 2028-04-01
GWP-L3-830 | GWP.06.05 | L3 | Manufacture & factory inspection (FAT): Composting equipment (blowers, turner, screen) | Task | Supplier | 194 | GWP-L3-670 FS | 2027-07-31 | 2028-03-13
GWP-L3-835 | GWP.06.06 | L3 | Dispatch & delivery at site: Composting equipment (blowers, turner, screen) | Task | Supplier | 12 | GWP-L3-830 FS | 2028-03-14 | 2028-03-27
GWP-L3-840 | GWP.06.07 | L3 | Manufacture & factory inspection (FAT): ETP skid, leachate & fire water pumps | Task | Supplier | 154 | GWP-L3-680 FS | 2027-09-22 | 2028-03-18
GWP-L3-845 | GWP.06.08 | L3 | Dispatch & delivery at site: ETP skid, leachate & fire water pumps | Task | Supplier | 12 | GWP-L3-840 FS | 2028-03-20 | 2028-04-01
GWP-L3-850 | GWP.06.09 | L3 | Manufacture & factory inspection (FAT): Transformer, HT/LT panels & DG set | Task | Supplier | 189 | GWP-L3-690 FS | 2027-09-04 | 2028-04-11
GWP-L3-855 | GWP.06.10 | L3 | Dispatch & delivery at site: Transformer, HT/LT panels & DG set | Task | Supplier | 12 | GWP-L3-850 FS | 2028-04-12 | 2028-04-25
GWP-L3-860 | GWP.06.11 | L3 | Manufacture & factory inspection (FAT): PLC/SCADA panels & field instruments | Task | Supplier | 234 | GWP-L3-695 FS | 2027-08-18 | 2028-05-16
GWP-L3-865 | GWP.06.12 | L3 | Dispatch & delivery at site: PLC/SCADA panels & field instruments | Task | Supplier | 12 | GWP-L3-860 FS | 2028-05-17 | 2028-05-30
GWP-PH-7 | GWP.07 | Phase | Construction (Contractor Package) |  |  | 250 |  | 2027-10-04 | 2028-07-20
GWP-L3-000 | GWP.07.01 | L3 | Site handover to construction contractor | Task | Company ABC | 1 | GWP-L3-640 FS; GWP-L3-370 FS; GWP-L3-270 FS; GWP-L3-450 FS; GWP-L3-320 FS; GWP-L3-330 FS | 2027-10-04 | 2027-10-04
GWP-L3-010 | GWP.07.02 | L3 | Site Mobilisation & Temporary Facilities | Fixed link | Construction contractor | 14 | Fixed: taken from L4-L6 Schedule workbook | 2027-10-04 | 2027-10-19
GWP-L3-020 | GWP.07.03 | L3 | Site Development & Enabling Works | Fixed link | Construction contractor | 166 | Fixed: taken from L4-L6 Schedule workbook | 2027-10-20 | 2028-04-29
GWP-L3-030 | GWP.07.04 | L3 | Civil Works - Process Buildings | Fixed link | Construction contractor | 70 | Fixed: taken from L4-L6 Schedule workbook | 2027-11-18 | 2028-02-07
GWP-L3-040 | GWP.07.05 | L3 | Civil Works - Composting Yard, RDF Shed & Leachate Tanks | Fixed link | Construction contractor | 38 | Fixed: taken from L4-L6 Schedule workbook | 2027-11-18 | 2027-12-31
GWP-L3-050 | GWP.07.06 | L3 | Civil Works - Administration & Utility Buildings | Fixed link | Construction contractor | 74 | Fixed: taken from L4-L6 Schedule workbook | 2027-11-18 | 2028-02-11
GWP-L3-060 | GWP.07.07 | L3 | Structural Steel Fabrication & Erection | Fixed link | Construction contractor | 110 | Fixed: taken from L4-L6 Schedule workbook | 2027-10-28 | 2028-03-03
GWP-L3-070 | GWP.07.08 | L3 | Mechanical Equipment Erection | Fixed link | Construction contractor | 22 | Fixed: taken from L4-L6 Schedule workbook | 2028-03-22 | 2028-04-15
GWP-L3-080 | GWP.07.09 | L3 | Piping, Fire Water & ETP Mechanical Works | Fixed link | Construction contractor | 163 | Fixed: taken from L4-L6 Schedule workbook | 2027-10-28 | 2028-05-04
GWP-L3-090 | GWP.07.10 | L3 | Electrical Installation | Fixed link | Construction contractor | 176 | Fixed: taken from L4-L6 Schedule workbook | 2027-11-27 | 2028-06-19
GWP-L3-100 | GWP.07.11 | L3 | Instrumentation & Automation Installation | Fixed link | Construction contractor | 107 | Fixed: taken from L4-L6 Schedule workbook | 2028-02-22 | 2028-06-24
GWP-L3-110 | GWP.07.12 | L3 | Construction Inspection, Testing & Mechanical Completion | Fixed link | Construction contractor | 119 | Fixed: taken from L4-L6 Schedule workbook | 2028-03-04 | 2028-07-20
GWP-L3-120 | GWP.07.13 | L3 | PMC site supervision, quality surveillance & progress monitoring | Task | PMC / Consultant | 250 | GWP-L3-000 SS; finishes with GWP-L3-110 | 2027-10-04 | 2028-07-20
GWP-PH-8 | GWP.08 | Phase | Completion, Pre-commissioning & Commissioning |  |  | 135 |  | 2028-07-19 | 2028-12-22
GWP-L3-900 | GWP.08.01 | L3 | Mechanical Completion of plant (all packages) | Milestone | PMC / Contractor | 0 | GWP-L3-110 FS; GWP-L3-815 FS; GWP-L3-825 FS; GWP-L3-835 FS; GWP-L3-845 FS; GWP-L3-855 FS; GWP-L3-865 FS | 2028-07-20 | 2028-07-20
GWP-L3-905 | GWP.08.02 | L3 | Grid power charging & HT energisation | Task | Company ABC | 5 | GWP-L3-385 FS; GWP-L3-420 FS | 2028-07-19 | 2028-07-24
GWP-L3-910 | GWP.08.03 | L3 | Pre-commissioning: flushing, cold runs, loop simulation & power-on | Task | Contractor / Suppliers | 30 | GWP-L3-900 FS; GWP-L3-905 FS; GWP-L3-440 FS; GWP-L3-480 FS | 2028-07-25 | 2028-08-28
GWP-L3-930 | GWP.08.04 | L3 | Vendor commissioning support & operator training | Task | Suppliers | 25 | GWP-L3-910 SS+10 | 2028-08-05 | 2028-09-02
GWP-L3-940 | GWP.08.05 | L3 | Hot commissioning: waste feed start-up & stabilisation | Task | Company ABC | 60 | GWP-L3-910 FS; GWP-L3-380 FS; GWP-L3-460 FS; GWP-L3-390 FS | 2028-08-29 | 2028-11-06
GWP-L3-950 | GWP.08.06 | L3 | Performance guarantee test run at rated capacity | Task | Company ABC | 40 | GWP-L3-940 FS | 2028-11-07 | 2028-12-22
GWP-L3-960 | GWP.08.07 | L3 | As-built drawings, O&M manuals & test records dossier | Task | PMC / Consultant | 50 | GWP-L3-940 SS+10 | 2028-09-09 | 2028-11-06
GWP-L3-970 | GWP.08.08 | L3 | Commissioning acceptance & handover to operations | Milestone | Company ABC | 0 | GWP-L3-950 FS; GWP-L3-960 FS; GWP-L3-930 FS | 2028-12-22 | 2028-12-22

## Key Dates
Key Dates and Consistency Checks
All dates are looked up from the L3 Schedule sheet.
Milestone | Activity ID | Date | Basis
Investment approval | GWP-L3-200 | 2027-01-01 | Finish
Land possession achieved | GWP-L3-270 | 2027-04-05 | Finish
Consent to Establish granted | GWP-L3-320 | 2027-07-13 | Finish
Letter of Award to construction contractor | GWP-L3-630 | 2027-09-15 | Finish
Contract signed | GWP-L3-640 | 2027-10-02 | Finish
Site handover to contractor | GWP-L3-000 | 2027-10-04 | Start
Structural steel IFC drawings released | GWP-L3-530 | 2027-10-27 | Finish
Delivery at site: trommel, conveyors, feed hopper, weighbridge | GWP-L3-815 | 2028-03-21 | Finish
Delivery at site: shredder & baling press | GWP-L3-825 | 2028-04-01 | Finish
Delivery at site: composting equipment | GWP-L3-835 | 2028-03-27 | Finish
Delivery at site: ETP skid & pumps | GWP-L3-845 | 2028-04-01 | Finish
Delivery at site: transformer, panels, DG | GWP-L3-855 | 2028-04-25 | Finish
Delivery at site: PLC/SCADA & instruments | GWP-L3-865 | 2028-05-30 | Finish
Mechanical Completion | GWP-L3-900 | 2028-07-20 | Finish
Grid power charged | GWP-L3-905 | 2028-07-24 | Finish
Consent to Operate obtained | GWP-L3-380 | 2028-08-24 | Finish
Pre-commissioning complete | GWP-L3-910 | 2028-08-28 | Finish
Commissioning acceptance & handover | GWP-L3-970 | 2028-12-22 | Finish
Checks
Handover date required by contractor L4-L6 schedule |  | 2027-10-04
Site handover date in this L3 schedule |  | 2027-10-04
Handover check |  | OK - handover is on or before required date
Months from approval to commissioning acceptance |  | 23.7
Working days of float to 31-Dec-2028 target |  | 7
Handover required date is the "Site handover" input of the L4-L6 Schedule workbook (Assumptions sheet). Update both if you change it.
Formulas:
Date = INDEX('L3 Schedule'!$J6:J97,MATCH([Activity ID],'L3 Schedule'!$A6:A97,0))
Date = INDEX('L3 Schedule'!$I6:I97,MATCH([Activity ID],'L3 Schedule'!$A6:A97,0))